## 1. Define
ID | Date Started | Date Completed | Cycle Time
TICKET-123 | 2017-06-01 | 2017-06-22 | 21 | Help
TICKET-456 | 2017-05-14 | 2017-05-16 | 2 | Measure your work item begin and end dates here. Remember: 1. Date started should be clearly defined as the time work begins on the ticket 2. Date completed should be when the story is released to production, or ends up in its final environment 3. Only measure items that flow all the way through to done. If an item is de-prioritized, then tag it and exclude from the calculations
TICKET-987 | 2017-06-15 | 2017-06-22 | 7
TICKET-546 | 2017-05-23 | 2017-05-31 | 8
TICKET-094 | 2017-06-01 | 2017-06-14 | 13
TICKET-566 | 2017-05-26 | 2017-06-01 | 6
TICKET-999 | 2017-06-02 | 2017-06-06 | 4
TICKET-332 | 2017-06-03 | 2017-06-10 | 7
TICKET-534 | 2017-05-10 | 2017-06-01 | 22
TICKET-900 | 2017-05-15 | 2017-06-03 | 19
Total |  |  | 10

## 2. Generate
Help
Nothing to do on this sheet! Just showing how we use a probability distribution to generate random inputs
Point #1 | Point #2 | Point #3 | Point #4 | Point #5 | Point #6 | Point #7 | Point #8 | Point #9 | Point #10
22 | 21 | 13 | 2 | 22 | 19 | 2 | 6 | 6 | 2
13 | 4 | 7 | 22 | 6 | 4 | 7 | 21 | 7 | 21
22 | 4 | 7 | 13 | 19 | 2 | 22 | 2 | 21 | 6
13 | 8 | 22 | 2 | 6 | 8 | 21 | 21 | 19 | 6
8 | 7 | 7 | 8 | 13 | 6 | 8 | 22 | 22 | 4
19 | 22 | 7 | 8 | 21 | 4 | 19 | 22 | 7 | 6
7 | 21 | 13 | 19 | 7 | 2 | 7 | 4 | 19 | 2
22 | 13 | 21 | 19 | 7 | 6 | 19 | 6 | 7 | 7
7 | 8 | 19 | 22 | 21 | 13 | 6 | 7 | 6 | 2
7 | 21 | 13 | 4 | 19 | 7 | 13 | 7 | 21 | 8
21 | 4 | 7 | 6 | 6 | 7 | 8 | 7 | 2 | 7
7 | 22 | 7 | 22 | 7 | 7 | 13 | 13 | 4 | 8
13 | 2 | 2 | 6 | 13 | 2 | 7 | 13 | 7 | 8
13 | 7 | 4 | 22 | 6 | 22 | 13 | 22 | 4 | 8
21 | 7 | 19 | 8 | 19 | 8 | 19 | 6 | 8 | 22
8 | 13 | 13 | 7 | 8 | 7 | 19 | 19 | 22 | 19
21 | 2 | 21 | 22 | 4 | 7 | 2 | 21 | 4 | 21
7 | 19 | 19 | 2 | 22 | 7 | 21 | 7 | 6 | 2
8 | 4 | 22 | 22 | 4 | 21 | 8 | 22 | 7 | 13
6 | 4 | 21 | 7 | 7 | 19 | 19 | 21 | 19 | 7
22 | 8 | 13 | 7 | 2 | 22 | 7 | 19 | 2 | 4
22 | 22 | 21 | 19 | 8 | 13 | 8 | 6 | 4 | 7
7 | 8 | 13 | 19 | 7 | 7 | 22 | 7 | 8 | 13
8 | 19 | 7 | 7 | 7 | 4 | 6 | 7 | 7 | 19
7 | 19 | 13 | 7 | 22 | 6 | 6 | 4 | 21 | 8
7 | 4 | 22 | 4 | 19 | 8 | 19 | 8 | 13 | 4
13 | 8 | 4 | 4 | 7 | 19 | 4 | 13 | 2 | 13
6 | 6 | 8 | 13 | 13 | 2 | 22 | 13 | 7 | 22
19 | 22 | 4 | 6 | 8 | 6 | 8 | 19 | 8 | 22
8 | 21 | 4 | 7 | 13 | 21 | 22 | 4 | 4 | 2
13 | 4 | 2 | 13 | 7 | 13 | 19 | 21 | 4 | 7
13 | 19 | 13 | 13 | 7 | 19 | 22 | 22 | 8 | 2
6 | 22 | 13 | 22 | 6 | 22 | 22 | 22 | 6 | 7
21 | 21 | 2 | 6 | 7 | 19 | 4 | 8 | 13 | 21
22 | 22 | 7 | 8 | 7 | 7 | 13 | 21 | 21 | 4
4 | 2 | 7 | 13 | 19 | 6 | 22 | 2 | 8 | 4
8 | 2 | 4 | 13 | 19 | 7 | 7 | 7 | 19 | 13
19 | 22 | 4 | 7 | 7 | 4 | 21 | 8 | 7 | 7
6 | 7 | 19 | 19 | 7 | 13 | 21 | 6 | 13 | 7
2 | 2 | 22 | 22 | 7 | 7 | 6 | 2 | 8 | 19
21 | 13 | 8 | 2 | 7 | 4 | 7 | 19 | 6 | 19
4 | 2 | 4 | 19 | 6 | 21 | 4 | 2 | 6 | 13
4 | 22 | 8 | 2 | 7 | 8 | 13 | 7 | 7 | 8
22 | 21 | 13 | 4 | 4 | 7 | 22 | 22 | 8 | 22
19 | 19 | 4 | 21 | 6 | 21 | 7 | 13 | 22 | 22
8 | 13 | 22 | 4 | 22 | 13 | 19 | 21 | 7 | 22
7 | 7 | 7 | 7 | 7 | 6 | 22 | 21 | 4 | 8
8 | 22 | 7 | 13 | 21 | 8 | 6 | 13 | 22 | 22
2 | 7 | 21 | 21 | 19 | 21 | 21 | 7 | 8 | 21
13 | 6 | 7 | 6 | 13 | 13 | 4 | 4 | 7 | 7
7 | 21 | 13 | 22 | 2 | 22 | 4 | 2 | 22 | 8
21 | 2 | 8 | 6 | 4 | 4 | 13 | 22 | 8 | 8
21 | 19 | 7 | 2 | 6 | 22 | 6 | 19 | 8 | 8
21 | 8 | 7 | 7 | 19 | 13 | 2 | 4 | 7 | 19
4 | 21 | 2 | 19 | 7 | 4 | 22 | 7 | 13 | 21
7 | 22 | 8 | 7 | 13 | 7 | 7 | 4 | 19 | 21
2 | 13 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 13
7 | 22 | 19 | 22 | 13 | 21 | 13 | 7 | 22 | 2
13 | 6 | 8 | 7 | 19 | 19 | 7 | 21 | 22 | 7
8 | 6 | 13 | 19 | 13 | 19 | 7 | 7 | 21 | 4
6 | 7 | 7 | 6 | 4 | 13 | 8 | 8 | 7 | 4
8 | 4 | 2 | 22 | 22 | 19 | 6 | 2 | 6 | 4
7 | 19 | 6 | 7 | 7 | 21 | 4 | 8 | 7 | 19
7 | 21 | 4 | 7 | 4 | 8 | 6 | 7 | 22 | 6
8 | 4 | 22 | 19 | 21 | 6 | 7 | 19 | 13 | 13
7 | 7 | 4 | 6 | 21 | 21 | 22 | 7 | 6 | 22
21 | 19 | 19 | 22 | 22 | 6 | 7 | 4 | 7 | 7
13 | 7 | 19 | 6 | 7 | 4 | 2 | 2 | 7 | 19
19 | 2 | 21 | 7 | 19 | 7 | 19 | 8 | 6 | 22
21 | 13 | 21 | 21 | 2 | 22 | 13 | 19 | 8 | 13
7 | 6 | 22 | 2 | 19 | 13 | 8 | 19 | 22 | 6
6 | 2 | 19 | 19 | 13 | 7 | 4 | 6 | 13 | 13
7 | 21 | 21 | 7 | 8 | 7 | 8 | 4 | 13 | 6
22 | 19 | 7 | 21 | 6 | 8 | 6 | 2 | 7 | 7
4 | 22 | 13 | 13 | 7 | 7 | 22 | 19 | 21 | 8
6 | 21 | 22 | 4 | 2 | 8 | 7 | 7 | 4 | 22
21 | 13 | 21 | 7 | 21 | 22 | 6 | 2 | 19 | 2
4 | 22 | 22 | 13 | 7 | 7 | 13 | 8 | 2 | 22
7 | 6 | 21 | 8 | 22 | 4 | 7 | 19 | 13 | 13
22 | 22 | 2 | 21 | 2 | 6 | 8 | 7 | 13 | 8
2 | 8 | 13 | 6 | 22 | 4 | 6 | 7 | 4 | 4
7 | 6 | 13 | 2 | 8 | 7 | 6 | 21 | 7 | 2
2 | 2 | 6 | 13 | 19 | 6 | 4 | 7 | 4 | 7
19 | 7 | 22 | 4 | 4 | 21 | 19 | 13 | 6 | 19
22 | 4 | 2 | 21 | 7 | 8 | 6 | 4 | 19 | 8
7 | 6 | 2 | 8 | 8 | 19 | 7 | 2 | 13 | 4
22 | 19 | 6 | 4 | 2 | 21 | 13 | 2 | 7 | 2
6 | 4 | 19 | 21 | 7 | 21 | 8 | 6 | 4 | 13
21 | 7 | 13 | 22 | 7 | 6 | 8 | 4 | 4 | 4
4 | 19 | 6 | 2 | 8 | 7 | 6 | 7 | 2 | 7
13 | 6 | 21 | 19 | 4 | 7 | 19 | 8 | 4 | 22
4 | 19 | 7 | 19 | 7 | 19 | 6 | 6 | 4 | 7
22 | 13 | 7 | 19 | 4 | 4 | 2 | 7 | 8 | 7
13 | 8 | 8 | 22 | 13 | 7 | 22 | 7 | 8 | 2
2 | 19 | 7 | 13 | 8 | 7 | 2 | 4 | 2 | 7
8 | 21 | 7 | 7 | 6 | 4 | 7 | 2 | 7 | 22
13 | 19 | 2 | 4 | 22 | 13 | 6 | 2 | 19 | 22
7 | 6 | 6 | 8 | 7 | 7 | 13 | 2 | 2 | 7
8 | 22 | 19 | 7 | 2 | 6 | 22 | 6 | 22 | 21
6 | 2 | 6 | 22 | 22 | 19 | 21 | 13 | 21 | 21
6 | 21 | 7 | 2 | 7 | 19 | 13 | 21 | 13 | 13
22 | 7 | 19 | 8 | 19 | 6 | 13 | 22 | 7 | 21
7 | 22 | 19 | 21 | 8 | 2 | 7 | 6 | 13 | 22
22 | 7 | 7 | 21 | 19 | 2 | 7 | 8 | 6 | 22
13 | 13 | 22 | 13 | 22 | 8 | 13 | 7 | 21 | 13
19 | 7 | 22 | 6 | 8 | 6 | 22 | 7 | 7 | 22
4 | 7 | 19 | 6 | 22 | 7 | 6 | 4 | 22 | 22
22 | 2 | 7 | 21 | 8 | 6 | 8 | 7 | 21 | 7
7 | 8 | 19 | 2 | 21 | 6 | 2 | 4 | 13 | 2
7 | 19 | 2 | 4 | 13 | 4 | 13 | 7 | 6 | 6
6 | 7 | 6 | 13 | 8 | 7 | 4 | 7 | 22 | 6
6 | 4 | 4 | 2 | 19 | 7 | 6 | 7 | 7 | 22
22 | 7 | 6 | 21 | 6 | 2 | 8 | 13 | 7 | 21
6 | 7 | 21 | 4 | 7 | 19 | 21 | 13 | 8 | 13
4 | 13 | 4 | 2 | 19 | 22 | 13 | 7 | 22 | 2
22 | 6 | 22 | 22 | 4 | 8 | 13 | 2 | 2 | 4
7 | 21 | 8 | 7 | 19 | 7 | 4 | 7 | 8 | 6
8 | 6 | 4 | 4 | 7 | 21 | 7 | 22 | 19 | 22
13 | 13 | 6 | 19 | 22 | 6 | 4 | 13 | 21 | 22
7 | 21 | 19 | 6 | 7 | 4 | 22 | 21 | 8 | 8
8 | 7 | 19 | 8 | 7 | 6 | 2 | 4 | 7 | 19
22 | 2 | 13 | 19 | 6 | 13 | 4 | 22 | 2 | 4
13 | 4 | 19 | 4 | 7 | 2 | 13 | 22 | 2 | 4
8 | 13 | 4 | 19 | 7 | 2 | 2 | 4 | 8 | 21
19 | 7 | 21 | 7 | 13 | 22 | 4 | 19 | 21 | 13
13 | 7 | 19 | 6 | 4 | 7 | 13 | 7 | 8 | 7
2 | 4 | 4 | 4 | 19 | 22 | 13 | 7 | 7 | 8
21 | 21 | 6 | 6 | 22 | 22 | 13 | 22 | 7 | 7
2 | 4 | 7 | 13 | 4 | 4 | 22 | 8 | 6 | 8
22 | 6 | 8 | 7 | 21 | 2 | 22 | 21 | 19 | 2
4 | 22 | 22 | 7 | 4 | 6 | 2 | 7 | 19 | 19
22 | 4 | 13 | 22 | 13 | 22 | 8 | 7 | 7 | 21
7 | 7 | 8 | 7 | 21 | 8 | 22 | 13 | 21 | 7
22 | 2 | 8 | 2 | 6 | 22 | 13 | 13 | 19 | 6
19 | 6 | 21 | 7 | 21 | 7 | 2 | 7 | 22 | 2
4 | 19 | 2 | 7 | 13 | 19 | 7 | 7 | 4 | 21
19 | 13 | 19 | 19 | 19 | 4 | 22 | 8 | 22 | 8
19 | 6 | 8 | 8 | 4 | 6 | 8 | 7 | 22 | 7
8 | 6 | 13 | 19 | 13 | 7 | 7 | 2 | 2 | 19
21 | 19 | 6 | 13 | 8 | 7 | 7 | 4 | 2 | 22
21 | 13 | 4 | 2 | 2 | 7 | 13 | 7 | 6 | 13
2 | 19 | 2 | 8 | 13 | 13 | 4 | 21 | 19 | 2
7 | 6 | 8 | 22 | 13 | 6 | 7 | 22 | 19 | 7
7 | 8 | 8 | 7 | 7 | 8 | 6 | 2 | 13 | 21
13 | 7 | 2 | 2 | 19 | 19 | 7 | 7 | 19 | 22
8 | 6 | 7 | 7 | 2 | 2 | 8 | 8 | 7 | 21
7 | 19 | 6 | 7 | 2 | 7 | 6 | 21 | 8 | 7
22 | 6 | 7 | 6 | 22 | 19 | 22 | 2 | 7 | 7
8 | 4 | 7 | 7 | 13 | 2 | 7 | 21 | 7 | 7
13 | 13 | 2 | 2 | 13 | 22 | 21 | 6 | 8 | 21
4 | 22 | 21 | 13 | 22 | 21 | 7 | 8 | 13 | 13
7 | 7 | 19 | 6 | 13 | 7 | 8 | 21 | 8 | 8
7 | 6 | 21 | 4 | 8 | 6 | 2 | 8 | 21 | 21
7 | 13 | 19 | 7 | 7 | 22 | 21 | 21 | 4 | 8
4 | 7 | 6 | 22 | 2 | 22 | 7 | 19 | 19 | 13
8 | 8 | 7 | 22 | 19 | 21 | 22 | 6 | 19 | 7
8 | 2 | 22 | 7 | 19 | 6 | 2 | 8 | 8 | 8
22 | 21 | 7 | 21 | 8 | 21 | 22 | 13 | 13 | 7
2 | 6 | 19 | 19 | 8 | 21 | 19 | 21 | 6 | 2
7 | 6 | 19 | 6 | 8 | 7 | 6 | 8 | 7 | 2
4 | 7 | 6 | 6 | 6 | 8 | 8 | 19 | 2 | 4
19 | 8 | 2 | 19 | 6 | 7 | 21 | 7 | 19 | 21
19 | 7 | 22 | 22 | 7 | 21 | 8 | 7 | 2 | 8
2 | 21 | 6 | 22 | 22 | 4 | 22 | 13 | 22 | 8
6 | 19 | 6 | 8 | 8 | 22 | 7 | 21 | 7 | 8
13 | 22 | 8 | 7 | 8 | 7 | 8 | 21 | 2 | 22
8 | 7 | 19 | 7 | 22 | 19 | 4 | 2 | 22 | 13
21 | 21 | 19 | 13 | 2 | 13 | 8 | 22 | 13 | 7
6 | 19 | 7 | 22 | 22 | 22 | 21 | 7 | 19 | 7
4 | 4 | 7 | 4 | 7 | 4 | 8 | 6 | 7 | 7
13 | 19 | 21 | 8 | 13 | 19 | 7 | 7 | 2 | 8
21 | 4 | 13 | 4 | 7 | 21 | 21 | 6 | 19 | 7
13 | 7 | 22 | 21 | 22 | 8 | 22 | 13 | 7 | 19
7 | 21 | 7 | 13 | 22 | 8 | 8 | 21 | 13 | 6
19 | 8 | 22 | 2 | 7 | 21 | 7 | 13 | 19 | 8
19 | 22 | 7 | 21 | 19 | 19 | 21 | 6 | 7 | 4
21 | 19 | 7 | 7 | 2 | 8 | 7 | 2 | 2 | 21
4 | 7 | 6 | 21 | 2 | 7 | 6 | 19 | 21 | 22
2 | 2 | 6 | 8 | 22 | 4 | 2 | 22 | 21 | 22
21 | 21 | 21 | 7 | 2 | 8 | 4 | 2 | 13 | 22
4 | 7 | 8 | 22 | 22 | 7 | 21 | 6 | 4 | 22
13 | 8 | 19 | 22 | 19 | 4 | 19 | 8 | 8 | 22
13 | 13 | 21 | 7 | 7 | 2 | 7 | 6 | 13 | 19
22 | 4 | 7 | 22 | 2 | 22 | 22 | 7 | 13 | 21
13 | 8 | 6 | 21 | 22 | 21 | 2 | 22 | 19 | 4
6 | 8 | 7 | 7 | 13 | 19 | 13 | 8 | 7 | 4
7 | 7 | 2 | 4 | 21 | 7 | 7 | 4 | 22 | 22
4 | 13 | 13 | 21 | 7 | 22 | 13 | 6 | 6 | 13
19 | 19 | 22 | 21 | 8 | 6 | 13 | 4 | 4 | 8
8 | 4 | 6 | 21 | 6 | 22 | 8 | 19 | 6 | 6
2 | 22 | 13 | 2 | 13 | 21 | 4 | 6 | 7 | 22
2 | 22 | 7 | 19 | 13 | 19 | 21 | 22 | 2 | 4
13 | 21 | 7 | 21 | 13 | 6 | 2 | 22 | 4 | 7
7 | 19 | 21 | 7 | 6 | 7 | 19 | 22 | 8 | 8
19 | 22 | 7 | 22 | 6 | 7 | 6 | 7 | 8 | 22
7 | 7 | 7 | 6 | 4 | 6 | 7 | 22 | 2 | 7
13 | 7 | 19 | 6 | 19 | 7 | 4 | 13 | 7 | 22
19 | 13 | 13 | 2 | 7 | 13 | 7 | 6 | 21 | 21
2 | 8 | 4 | 13 | 13 | 2 | 6 | 4 | 8 | 21
6 | 19 | 13 | 13 | 22 | 19 | 6 | 22 | 19 | 22
8 | 8 | 8 | 7 | 2 | 19 | 13 | 19 | 7 | 4
8 | 7 | 22 | 4 | 19 | 19 | 6 | 8 | 21 | 19
21 | 8 | 2 | 21 | 13 | 2 | 13 | 21 | 21 | 8
13 | 22 | 2 | 2 | 6 | 4 | 19 | 2 | 2 | 8
7 | 7 | 7 | 13 | 4 | 6 | 6 | 7 | 4 | 2
7 | 7 | 4 | 19 | 7 | 21 | 7 | 21 | 4 | 7
22 | 22 | 7 | 4 | 21 | 7 | 2 | 21 | 8 | 4
2 | 7 | 2 | 19 | 7 | 13 | 4 | 13 | 19 | 8
7 | 19 | 4 | 19 | 7 | 19 | 13 | 7 | 8 | 2
2 | 7 | 21 | 4 | 7 | 4 | 19 | 4 | 6 | 6
19 | 7 | 19 | 22 | 7 | 13 | 13 | 2 | 22 | 8
13 | 7 | 22 | 2 | 7 | 2 | 7 | 4 | 4 | 2
2 | 2 | 7 | 6 | 7 | 7 | 22 | 2 | 2 | 7
7 | 21 | 21 | 13 | 21 | 7 | 22 | 4 | 8 | 7
7 | 7 | 2 | 19 | 7 | 13 | 6 | 19 | 8 | 7
19 | 7 | 13 | 22 | 22 | 6 | 8 | 22 | 13 | 8
8 | 7 | 2 | 7 | 13 | 7 | 7 | 13 | 2 | 21
22 | 19 | 8 | 19 | 13 | 8 | 2 | 7 | 7 | 4
7 | 4 | 2 | 4 | 6 | 7 | 7 | 19 | 4 | 21
19 | 2 | 22 | 6 | 7 | 19 | 21 | 21 | 13 | 21
4 | 6 | 19 | 19 | 8 | 8 | 6 | 2 | 4 | 19
8 | 8 | 22 | 8 | 13 | 7 | 22 | 8 | 19 | 4
19 | 4 | 7 | 22 | 13 | 22 | 7 | 7 | 22 | 7
22 | 2 | 22 | 19 | 7 | 7 | 6 | 2 | 7 | 2
2 | 7 | 7 | 7 | 13 | 7 | 13 | 21 | 2 | 7
4 | 19 | 8 | 21 | 8 | 21 | 8 | 22 | 8 | 19
4 | 8 | 22 | 8 | 4 | 4 | 4 | 19 | 7 | 6
13 | 7 | 19 | 8 | 4 | 22 | 8 | 21 | 7 | 2
19 | 7 | 2 | 4 | 7 | 22 | 21 | 2 | 6 | 19
2 | 8 | 4 | 7 | 19 | 7 | 22 | 21 | 8 | 6
13 | 4 | 7 | 6 | 13 | 21 | 2 | 19 | 21 | 7
7 | 4 | 4 | 19 | 7 | 7 | 8 | 13 | 8 | 4
4 | 7 | 6 | 4 | 7 | 2 | 19 | 22 | 6 | 21
4 | 22 | 7 | 6 | 13 | 4 | 7 | 13 | 7 | 19
2 | 19 | 6 | 21 | 7 | 8 | 2 | 21 | 19 | 2
22 | 7 | 19 | 7 | 7 | 13 | 4 | 22 | 6 | 7
7 | 22 | 13 | 7 | 13 | 22 | 8 | 21 | 19 | 7
6 | 2 | 4 | 13 | 4 | 13 | 7 | 13 | 8 | 21
21 | 2 | 13 | 19 | 22 | 19 | 22 | 7 | 7 | 13
4 | 6 | 19 | 6 | 13 | 4 | 7 | 4 | 2 | 6
21 | 22 | 22 | 19 | 6 | 4 | 2 | 21 | 6 | 21
19 | 21 | 13 | 19 | 19 | 4 | 2 | 2 | 7 | 21
7 | 4 | 19 | 4 | 13 | 22 | 21 | 7 | 7 | 7
2 | 7 | 7 | 2 | 4 | 6 | 21 | 6 | 2 | 4
2 | 6 | 22 | 13 | 13 | 13 | 7 | 4 | 19 | 7
2 | 6 | 7 | 21 | 4 | 13 | 22 | 21 | 7 | 22
7 | 22 | 21 | 22 | 4 | 13 | 8 | 7 | 7 | 22
21 | 2 | 22 | 19 | 22 | 7 | 8 | 19 | 19 | 19
6 | 8 | 4 | 2 | 2 | 4 | 7 | 6 | 13 | 7
13 | 7 | 7 | 7 | 13 | 19 | 21 | 7 | 6 | 8
7 | 2 | 7 | 4 | 21 | 22 | 22 | 19 | 7 | 13
4 | 2 | 8 | 8 | 4 | 7 | 7 | 7 | 7 | 22
19 | 7 | 7 | 8 | 7 | 7 | 7 | 4 | 19 | 7
2 | 4 | 22 | 7 | 13 | 8 | 21 | 7 | 7 | 13
22 | 13 | 22 | 7 | 7 | 7 | 6 | 19 | 22 | 4
7 | 4 | 19 | 22 | 7 | 8 | 4 | 4 | 7 | 22
4 | 13 | 7 | 13 | 13 | 8 | 22 | 4 | 2 | 2
7 | 7 | 19 | 19 | 21 | 7 | 19 | 7 | 6 | 7
7 | 19 | 21 | 21 | 7 | 7 | 21 | 7 | 8 | 2
21 | 22 | 7 | 2 | 19 | 21 | 8 | 4 | 8 | 21
7 | 19 | 7 | 7 | 21 | 7 | 7 | 21 | 7 | 22
13 | 2 | 7 | 7 | 6 | 21 | 6 | 7 | 4 | 21
7 | 2 | 7 | 7 | 6 | 13 | 6 | 7 | 7 | 2
7 | 2 | 13 | 2 | 19 | 4 | 4 | 7 | 13 | 7
8 | 19 | 13 | 22 | 7 | 4 | 6 | 8 | 13 | 6
19 | 7 | 2 | 22 | 19 | 19 | 4 | 6 | 6 | 8
4 | 13 | 8 | 21 | 7 | 7 | 7 | 22 | 13 | 21
4 | 19 | 7 | 19 | 7 | 2 | 21 | 22 | 7 | 13
22 | 7 | 22 | 13 | 8 | 4 | 22 | 13 | 22 | 8
7 | 8 | 2 | 22 | 19 | 8 | 19 | 6 | 19 | 4
7 | 13 | 19 | 6 | 6 | 21 | 7 | 7 | 13 | 4
7 | 21 | 13 | 19 | 7 | 6 | 7 | 7 | 22 | 6
2 | 7 | 21 | 13 | 13 | 4 | 2 | 21 | 19 | 21
22 | 19 | 7 | 6 | 8 | 6 | 8 | 22 | 13 | 4
19 | 21 | 13 | 6 | 2 | 2 | 4 | 21 | 2 | 22
7 | 19 | 4 | 2 | 8 | 6 | 13 | 6 | 19 | 22
21 | 4 | 8 | 19 | 4 | 21 | 4 | 4 | 21 | 22
19 | 21 | 7 | 22 | 7 | 22 | 13 | 21 | 19 | 19
4 | 4 | 7 | 21 | 13 | 6 | 22 | 6 | 22 | 8
7 | 6 | 13 | 22 | 8 | 13 | 19 | 13 | 7 | 6
21 | 22 | 8 | 8 | 2 | 6 | 21 | 19 | 19 | 7
19 | 7 | 4 | 7 | 21 | 4 | 7 | 8 | 2 | 7
7 | 13 | 7 | 7 | 7 | 2 | 7 | 8 | 21 | 8
22 | 19 | 4 | 8 | 19 | 7 | 7 | 2 | 21 | 19
2 | 21 | 7 | 7 | 13 | 7 | 6 | 2 | 7 | 4
19 | 2 | 2 | 21 | 22 | 7 | 7 | 8 | 4 | 6
21 | 6 | 21 | 13 | 7 | 13 | 19 | 13 | 4 | 4
7 | 7 | 19 | 2 | 2 | 2 | 2 | 22 | 4 | 7
22 | 22 | 2 | 7 | 19 | 21 | 8 | 13 | 22 | 22
21 | 22 | 19 | 7 | 13 | 6 | 19 | 13 | 7 | 22
6 | 8 | 4 | 2 | 7 | 2 | 21 | 22 | 7 | 7
7 | 19 | 22 | 19 | 6 | 4 | 19 | 19 | 8 | 21
22 | 7 | 21 | 2 | 7 | 21 | 21 | 19 | 22 | 7
22 | 4 | 8 | 13 | 6 | 7 | 8 | 6 | 2 | 4
8 | 19 | 21 | 19 | 2 | 2 | 21 | 19 | 4 | 2
2 | 21 | 22 | 8 | 13 | 6 | 7 | 13 | 4 | 2
13 | 19 | 7 | 21 | 19 | 4 | 4 | 19 | 8 | 8
2 | 19 | 8 | 8 | 7 | 7 | 2 | 22 | 8 | 7
7 | 7 | 21 | 22 | 8 | 13 | 8 | 19 | 2 | 6
13 | 4 | 7 | 8 | 22 | 8 | 22 | 2 | 21 | 7
4 | 21 | 21 | 22 | 21 | 8 | 13 | 6 | 8 | 7
22 | 7 | 19 | 7 | 2 | 7 | 8 | 7 | 8 | 8
2 | 13 | 21 | 7 | 7 | 2 | 19 | 8 | 4 | 21
21 | 19 | 7 | 2 | 19 | 21 | 7 | 4 | 4 | 6
19 | 13 | 8 | 8 | 19 | 22 | 2 | 21 | 2 | 2
21 | 4 | 13 | 21 | 7 | 21 | 21 | 6 | 2 | 2
8 | 8 | 6 | 4 | 19 | 8 | 6 | 7 | 22 | 13
13 | 22 | 2 | 6 | 8 | 2 | 7 | 13 | 19 | 7
13 | 7 | 13 | 21 | 7 | 21 | 13 | 2 | 7 | 6
21 | 13 | 13 | 21 | 19 | 13 | 19 | 22 | 2 | 21
21 | 7 | 7 | 19 | 13 | 21 | 4 | 8 | 19 | 6
13 | 4 | 22 | 6 | 21 | 7 | 6 | 21 | 6 | 22
7 | 19 | 6 | 21 | 13 | 7 | 7 | 13 | 13 | 7
6 | 7 | 7 | 13 | 2 | 2 | 8 | 2 | 7 | 8
13 | 19 | 13 | 21 | 7 | 19 | 7 | 2 | 8 | 21
21 | 19 | 19 | 21 | 4 | 22 | 13 | 6 | 7 | 19
8 | 7 | 21 | 13 | 2 | 8 | 6 | 8 | 8 | 22
4 | 7 | 19 | 22 | 6 | 21 | 2 | 7 | 7 | 4
22 | 19 | 4 | 4 | 4 | 21 | 7 | 22 | 7 | 19
13 | 21 | 22 | 2 | 19 | 7 | 4 | 13 | 8 | 2
7 | 4 | 7 | 4 | 8 | 22 | 7 | 22 | 4 | 4
6 | 13 | 22 | 8 | 8 | 2 | 4 | 4 | 4 | 4
21 | 13 | 7 | 19 | 6 | 8 | 8 | 7 | 8 | 7
22 | 4 | 19 | 21 | 4 | 13 | 7 | 7 | 2 | 22
7 | 7 | 21 | 7 | 8 | 19 | 19 | 8 | 6 | 13
8 | 21 | 2 | 8 | 19 | 4 | 2 | 13 | 7 | 22
8 | 22 | 7 | 7 | 7 | 22 | 4 | 19 | 13 | 13
6 | 21 | 7 | 13 | 7 | 7 | 19 | 2 | 2 | 4
21 | 6 | 7 | 22 | 22 | 21 | 6 | 7 | 7 | 21
22 | 4 | 19 | 4 | 13 | 13 | 8 | 4 | 19 | 2
7 | 4 | 4 | 22 | 6 | 22 | 7 | 6 | 19 | 4
22 | 13 | 8 | 22 | 6 | 13 | 7 | 6 | 7 | 4
8 | 7 | 19 | 19 | 8 | 7 | 21 | 7 | 7 | 7
13 | 4 | 22 | 19 | 19 | 4 | 8 | 21 | 19 | 21
21 | 8 | 2 | 4 | 21 | 4 | 13 | 8 | 4 | 8
13 | 4 | 8 | 6 | 4 | 2 | 2 | 19 | 21 | 4
13 | 21 | 22 | 7 | 21 | 7 | 22 | 13 | 19 | 7
2 | 6 | 21 | 22 | 7 | 6 | 13 | 6 | 6 | 21
19 | 13 | 21 | 19 | 21 | 7 | 19 | 6 | 2 | 4
7 | 2 | 13 | 21 | 19 | 7 | 13 | 4 | 2 | 6
7 | 2 | 6 | 7 | 21 | 7 | 8 | 8 | 7 | 6
7 | 19 | 4 | 13 | 2 | 6 | 21 | 7 | 7 | 6
7 | 7 | 2 | 2 | 7 | 19 | 13 | 7 | 4 | 21
8 | 7 | 22 | 21 | 8 | 19 | 7 | 6 | 7 | 22
2 | 13 | 22 | 19 | 21 | 8 | 7 | 7 | 4 | 19
21 | 21 | 8 | 21 | 4 | 7 | 2 | 19 | 7 | 4
7 | 6 | 13 | 7 | 4 | 6 | 22 | 13 | 22 | 19
8 | 8 | 19 | 21 | 2 | 21 | 22 | 4 | 4 | 22
7 | 7 | 7 | 19 | 7 | 2 | 19 | 6 | 7 | 7
2 | 8 | 21 | 2 | 13 | 22 | 22 | 13 | 21 | 22
6 | 6 | 21 | 13 | 7 | 22 | 13 | 7 | 2 | 2
8 | 6 | 2 | 19 | 7 | 2 | 4 | 22 | 21 | 2
8 | 19 | 8 | 21 | 19 | 21 | 21 | 8 | 22 | 7
7 | 6 | 2 | 6 | 7 | 7 | 22 | 4 | 21 | 13
21 | 13 | 6 | 7 | 6 | 22 | 7 | 2 | 19 | 8
21 | 2 | 6 | 8 | 4 | 4 | 21 | 19 | 21 | 7
7 | 21 | 21 | 8 | 22 | 4 | 2 | 7 | 6 | 7
13 | 19 | 6 | 7 | 21 | 4 | 6 | 19 | 8 | 7
13 | 8 | 21 | 6 | 19 | 6 | 7 | 7 | 4 | 8
8 | 13 | 8 | 21 | 19 | 7 | 6 | 22 | 6 | 19
13 | 7 | 13 | 7 | 21 | 8 | 19 | 8 | 6 | 8
4 | 7 | 6 | 6 | 4 | 4 | 19 | 7 | 19 | 22
2 | 4 | 7 | 19 | 4 | 13 | 19 | 7 | 2 | 21
21 | 7 | 7 | 6 | 19 | 4 | 19 | 19 | 7 | 7
21 | 2 | 13 | 13 | 21 | 21 | 8 | 22 | 7 | 21
4 | 4 | 21 | 13 | 7 | 19 | 7 | 4 | 21 | 19
2 | 21 | 6 | 22 | 8 | 7 | 7 | 19 | 8 | 8
6 | 8 | 2 | 22 | 2 | 4 | 7 | 8 | 7 | 4
7 | 7 | 19 | 22 | 8 | 7 | 2 | 8 | 19 | 8
2 | 8 | 21 | 8 | 7 | 21 | 8 | 8 | 21 | 13
21 | 8 | 21 | 7 | 4 | 19 | 2 | 8 | 22 | 21
6 | 7 | 7 | 2 | 2 | 7 | 21 | 19 | 7 | 4
4 | 8 | 6 | 7 | 13 | 22 | 21 | 4 | 2 | 7
7 | 4 | 6 | 7 | 8 | 6 | 8 | 2 | 8 | 7
8 | 21 | 7 | 19 | 6 | 19 | 4 | 7 | 6 | 21
19 | 13 | 4 | 7 | 21 | 4 | 7 | 6 | 8 | 8
13 | 21 | 7 | 13 | 22 | 2 | 6 | 13 | 6 | 7
22 | 22 | 21 | 7 | 2 | 7 | 13 | 7 | 21 | 19
2 | 13 | 21 | 7 | 4 | 21 | 19 | 2 | 4 | 13
19 | 22 | 8 | 7 | 7 | 21 | 6 | 22 | 4 | 13
4 | 13 | 13 | 7 | 22 | 22 | 4 | 2 | 19 | 7
8 | 19 | 8 | 7 | 19 | 19 | 2 | 4 | 7 | 7
13 | 19 | 22 | 22 | 19 | 22 | 21 | 4 | 22 | 6
22 | 6 | 7 | 2 | 4 | 22 | 13 | 7 | 2 | 13
19 | 4 | 2 | 13 | 6 | 6 | 8 | 6 | 8 | 21
2 | 2 | 2 | 13 | 7 | 22 | 21 | 7 | 19 | 2
7 | 19 | 7 | 21 | 19 | 7 | 21 | 2 | 7 | 21
7 | 19 | 7 | 6 | 22 | 2 | 13 | 7 | 7 | 7
2 | 21 | 8 | 7 | 7 | 4 | 2 | 2 | 4 | 7
7 | 8 | 21 | 4 | 8 | 8 | 19 | 7 | 4 | 2
4 | 7 | 2 | 6 | 7 | 21 | 8 | 13 | 8 | 4
13 | 7 | 13 | 6 | 21 | 7 | 7 | 19 | 4 | 13
6 | 7 | 7 | 13 | 7 | 7 | 19 | 19 | 19 | 13
6 | 21 | 22 | 13 | 13 | 6 | 7 | 7 | 7 | 6
6 | 6 | 21 | 19 | 2 | 22 | 8 | 7 | 22 | 4
7 | 6 | 6 | 6 | 13 | 13 | 7 | 7 | 7 | 13
4 | 13 | 7 | 19 | 4 | 22 | 4 | 6 | 13 | 7
7 | 6 | 2 | 19 | 4 | 4 | 4 | 7 | 6 | 8
4 | 19 | 2 | 7 | 7 | 19 | 4 | 8 | 21 | 2
4 | 7 | 7 | 2 | 8 | 19 | 7 | 22 | 7 | 13
13 | 7 | 13 | 4 | 21 | 7 | 2 | 7 | 7 | 13
7 | 13 | 13 | 13 | 19 | 6 | 7 | 19 | 21 | 8
19 | 7 | 21 | 7 | 4 | 6 | 22 | 7 | 7 | 7
22 | 21 | 13 | 7 | 6 | 13 | 21 | 21 | 7 | 19
7 | 4 | 8 | 4 | 8 | 19 | 19 | 21 | 8 | 2
19 | 4 | 7 | 13 | 22 | 13 | 13 | 6 | 7 | 21
7 | 13 | 8 | 7 | 21 | 13 | 19 | 22 | 2 | 19
8 | 4 | 6 | 7 | 8 | 19 | 8 | 22 | 2 | 19
4 | 19 | 4 | 7 | 2 | 7 | 21 | 4 | 7 | 13
13 | 22 | 4 | 7 | 2 | 7 | 7 | 6 | 8 | 8
8 | 19 | 4 | 7 | 7 | 7 | 21 | 22 | 4 | 19
22 | 8 | 13 | 13 | 21 | 8 | 13 | 21 | 19 | 19
2 | 13 | 4 | 7 | 7 | 22 | 2 | 2 | 8 | 2
4 | 8 | 6 | 13 | 6 | 13 | 4 | 7 | 6 | 7
19 | 7 | 8 | 7 | 7 | 22 | 13 | 2 | 6 | 4
19 | 13 | 2 | 2 | 22 | 2 | 4 | 6 | 21 | 2
7 | 19 | 7 | 6 | 2 | 4 | 7 | 6 | 13 | 7
13 | 6 | 21 | 7 | 2 | 22 | 6 | 6 | 2 | 19
22 | 19 | 22 | 7 | 4 | 7 | 19 | 22 | 7 | 19
7 | 21 | 4 | 7 | 22 | 7 | 4 | 7 | 2 | 21
19 | 7 | 22 | 19 | 7 | 2 | 4 | 21 | 7 | 8
6 | 22 | 7 | 4 | 2 | 8 | 6 | 7 | 19 | 8
21 | 22 | 22 | 22 | 19 | 2 | 7 | 19 | 21 | 4
13 | 7 | 8 | 22 | 22 | 8 | 6 | 2 | 21 | 4
19 | 7 | 19 | 6 | 2 | 22 | 19 | 13 | 6 | 7
19 | 4 | 8 | 21 | 19 | 13 | 7 | 13 | 7 | 21
8 | 13 | 2 | 7 | 22 | 19 | 7 | 22 | 6 | 21
19 | 7 | 7 | 13 | 21 | 6 | 7 | 7 | 19 | 19
6 | 2 | 19 | 6 | 22 | 22 | 8 | 8 | 21 | 19
22 | 21 | 7 | 8 | 8 | 22 | 22 | 19 | 22 | 13
4 | 7 | 7 | 8 | 21 | 21 | 21 | 7 | 21 | 8
19 | 7 | 19 | 19 | 7 | 21 | 6 | 13 | 21 | 13
4 | 19 | 7 | 7 | 2 | 6 | 19 | 21 | 7 | 21
7 | 6 | 7 | 19 | 7 | 2 | 6 | 2 | 19 | 13
21 | 7 | 8 | 4 | 2 | 19 | 6 | 8 | 6 | 6
13 | 13 | 8 | 6 | 4 | 21 | 8 | 7 | 21 | 21
4 | 7 | 4 | 2 | 21 | 8 | 6 | 4 | 6 | 7
7 | 22 | 7 | 21 | 21 | 13 | 13 | 6 | 19 | 13
8 | 7 | 4 | 4 | 8 | 13 | 22 | 19 | 22 | 19
6 | 22 | 13 | 13 | 7 | 2 | 2 | 19 | 4 | 13
21 | 7 | 2 | 4 | 8 | 21 | 7 | 13 | 21 | 4
7 | 22 | 19 | 13 | 13 | 4 | 7 | 4 | 22 | 21
19 | 19 | 8 | 6 | 4 | 7 | 6 | 13 | 8 | 6
19 | 6 | 4 | 4 | 8 | 22 | 4 | 4 | 13 | 6
8 | 2 | 13 | 7 | 22 | 19 | 4 | 7 | 19 | 19
7 | 2 | 7 | 7 | 4 | 2 | 6 | 8 | 22 | 22
4 | 13 | 21 | 21 | 21 | 22 | 4 | 21 | 8 | 7
7 | 21 | 2 | 19 | 13 | 7 | 4 | 8 | 8 | 7
8 | 19 | 7 | 21 | 2 | 19 | 22 | 4 | 7 | 8
6 | 7 | 22 | 21 | 2 | 19 | 13 | 22 | 22 | 13
19 | 21 | 2 | 7 | 2 | 8 | 6 | 4 | 22 | 2
19 | 22 | 13 | 2 | 4 | 4 | 13 | 8 | 2 | 2
7 | 22 | 2 | 4 | 22 | 2 | 22 | 4 | 6 | 4
7 | 2 | 2 | 6 | 21 | 7 | 7 | 19 | 19 | 7
22 | 4 | 6 | 19 | 7 | 19 | 6 | 2 | 8 | 4
2 | 8 | 13 | 19 | 22 | 7 | 13 | 8 | 7 | 8
21 | 8 | 19 | 19 | 7 | 19 | 13 | 21 | 7 | 7
13 | 19 | 6 | 2 | 4 | 22 | 19 | 22 | 13 | 2
7 | 4 | 6 | 22 | 22 | 6 | 13 | 8 | 19 | 6
13 | 6 | 8 | 7 | 13 | 7 | 19 | 2 | 2 | 21
7 | 4 | 8 | 2 | 7 | 2 | 21 | 13 | 4 | 7
22 | 21 | 6 | 21 | 8 | 19 | 22 | 19 | 7 | 8
22 | 21 | 13 | 2 | 13 | 19 | 19 | 2 | 8 | 6
22 | 13 | 22 | 22 | 21 | 7 | 7 | 8 | 21 | 8
7 | 21 | 6 | 22 | 7 | 2 | 7 | 7 | 21 | 6
2 | 4 | 13 | 19 | 7 | 8 | 6 | 6 | 19 | 6
7 | 19 | 8 | 7 | 13 | 22 | 21 | 2 | 21 | 2
19 | 13 | 6 | 7 | 8 | 22 | 13 | 4 | 2 | 13
7 | 4 | 6 | 7 | 2 | 6 | 6 | 4 | 6 | 4
8 | 19 | 13 | 21 | 21 | 19 | 8 | 22 | 22 | 2
21 | 8 | 2 | 6 | 6 | 7 | 4 | 7 | 19 | 6
4 | 4 | 8 | 8 | 7 | 19 | 22 | 6 | 7 | 2
21 | 4 | 13 | 7 | 7 | 8 | 2 | 7 | 8 | 7
2 | 13 | 4 | 21 | 7 | 2 | 2 | 7 | 6 | 4
6 | 6 | 7 | 6 | 7 | 4 | 8 | 2 | 7 | 8
21 | 21 | 7 | 6 | 13 | 7 | 13 | 13 | 6 | 6
19 | 7 | 8 | 6 | 6 | 2 | 21 | 21 | 21 | 7
13 | 6 | 13 | 8 | 13 | 2 | 6 | 19 | 13 | 7
4 | 2 | 21 | 7 | 6 | 4 | 6 | 2 | 13 | 6
13 | 19 | 8 | 21 | 2 | 2 | 2 | 19 | 7 | 2
13 | 21 | 2 | 2 | 7 | 13 | 7 | 4 | 7 | 8
8 | 2 | 22 | 21 | 7 | 7 | 13 | 2 | 7 | 13
19 | 7 | 22 | 21 | 21 | 8 | 2 | 21 | 8 | 13
21 | 13 | 6 | 4 | 13 | 19 | 22 | 21 | 7 | 13
13 | 22 | 13 | 21 | 7 | 21 | 6 | 13 | 8 | 8
13 | 13 | 4 | 19 | 19 | 7 | 22 | 8 | 22 | 7
22 | 2 | 21 | 6 | 13 | 2 | 8 | 22 | 21 | 4
4 | 21 | 7 | 6 | 19 | 4 | 4 | 19 | 2 | 8
6 | 4 | 22 | 19 | 22 | 7 | 2 | 8 | 7 | 7
7 | 19 | 19 | 22 | 4 | 21 | 22 | 19 | 7 | 22
2 | 13 | 13 | 8 | 7 | 6 | 4 | 8 | 7 | 19
4 | 2 | 6 | 22 | 19 | 21 | 7 | 7 | 13 | 8
21 | 13 | 13 | 21 | 8 | 2 | 13 | 13 | 2 | 8
6 | 19 | 7 | 13 | 21 | 13 | 22 | 21 | 7 | 21
7 | 7 | 19 | 19 | 4 | 7 | 6 | 22 | 21 | 7
4 | 4 | 7 | 4 | 7 | 2 | 19 | 6 | 13 | 8
21 | 2 | 21 | 8 | 8 | 19 | 8 | 6 | 21 | 7
4 | 19 | 6 | 19 | 2 | 22 | 4 | 22 | 7 | 19
21 | 22 | 6 | 7 | 2 | 7 | 22 | 6 | 2 | 4
2 | 22 | 21 | 6 | 13 | 8 | 7 | 13 | 7 | 21
21 | 6 | 7 | 8 | 2 | 19 | 7 | 2 | 7 | 22
7 | 21 | 21 | 7 | 6 | 2 | 7 | 22 | 4 | 13
7 | 6 | 7 | 4 | 8 | 22 | 8 | 19 | 2 | 2
8 | 8 | 8 | 8 | 21 | 8 | 6 | 21 | 7 | 7
2 | 2 | 8 | 19 | 22 | 6 | 22 | 21 | 8 | 4
7 | 6 | 2 | 13 | 6 | 19 | 7 | 7 | 8 | 21
7 | 4 | 8 | 22 | 7 | 7 | 6 | 2 | 19 | 22
19 | 21 | 19 | 7 | 6 | 7 | 2 | 2 | 6 | 7
21 | 21 | 7 | 13 | 6 | 19 | 8 | 19 | 21 | 7
4 | 19 | 2 | 4 | 4 | 6 | 22 | 7 | 21 | 7
7 | 7 | 2 | 7 | 2 | 8 | 19 | 8 | 6 | 2
4 | 22 | 4 | 19 | 21 | 7 | 13 | 6 | 21 | 21
2 | 22 | 7 | 7 | 8 | 13 | 7 | 19 | 7 | 21
6 | 7 | 22 | 21 | 22 | 6 | 8 | 8 | 19 | 13
8 | 21 | 6 | 13 | 8 | 2 | 19 | 7 | 13 | 7
7 | 19 | 7 | 19 | 7 | 13 | 22 | 13 | 13 | 2
21 | 19 | 13 | 7 | 2 | 2 | 19 | 21 | 7 | 8
22 | 7 | 7 | 7 | 7 | 22 | 6 | 13 | 19 | 4
8 | 4 | 19 | 6 | 8 | 22 | 4 | 22 | 6 | 19
4 | 13 | 7 | 6 | 22 | 6 | 22 | 6 | 2 | 6
4 | 19 | 7 | 8 | 19 | 4 | 4 | 22 | 7 | 6
6 | 4 | 21 | 7 | 2 | 7 | 19 | 7 | 4 | 2
7 | 8 | 6 | 2 | 4 | 7 | 19 | 19 | 7 | 8
7 | 22 | 7 | 19 | 13 | 4 | 21 | 21 | 8 | 7
4 | 21 | 13 | 19 | 7 | 6 | 19 | 7 | 6 | 2
8 | 22 | 2 | 13 | 8 | 21 | 13 | 8 | 19 | 13
8 | 6 | 6 | 4 | 7 | 7 | 8 | 2 | 7 | 19
13 | 19 | 22 | 6 | 7 | 7 | 6 | 7 | 7 | 4
19 | 13 | 22 | 7 | 7 | 7 | 22 | 6 | 19 | 21
21 | 19 | 21 | 22 | 2 | 19 | 8 | 19 | 19 | 6
7 | 6 | 13 | 8 | 7 | 4 | 7 | 13 | 8 | 21
21 | 2 | 2 | 6 | 7 | 8 | 7 | 4 | 7 | 22
7 | 4 | 8 | 22 | 7 | 8 | 4 | 21 | 4 | 21
6 | 22 | 2 | 2 | 22 | 7 | 7 | 19 | 6 | 4
13 | 21 | 22 | 7 | 8 | 7 | 22 | 8 | 13 | 19
21 | 21 | 2 | 2 | 19 | 22 | 21 | 13 | 21 | 6
21 | 6 | 4 | 2 | 21 | 19 | 8 | 7 | 21 | 7
19 | 13 | 19 | 7 | 21 | 7 | 4 | 4 | 6 | 7
8 | 4 | 19 | 21 | 4 | 22 | 2 | 7 | 13 | 2
7 | 7 | 21 | 6 | 7 | 19 | 19 | 21 | 7 | 2
7 | 7 | 22 | 6 | 6 | 19 | 2 | 21 | 7 | 2
2 | 4 | 22 | 6 | 19 | 4 | 19 | 4 | 7 | 2
21 | 4 | 22 | 4 | 13 | 13 | 19 | 4 | 8 | 7
13 | 13 | 8 | 6 | 7 | 8 | 13 | 7 | 7 | 8
7 | 8 | 7 | 19 | 19 | 6 | 7 | 22 | 4 | 6
13 | 8 | 13 | 19 | 7 | 19 | 4 | 7 | 7 | 21
7 | 13 | 6 | 21 | 4 | 22 | 22 | 7 | 6 | 7
2 | 21 | 4 | 13 | 19 | 13 | 2 | 7 | 21 | 7
7 | 19 | 7 | 22 | 4 | 6 | 7 | 8 | 19 | 19
19 | 19 | 6 | 21 | 6 | 13 | 2 | 2 | 7 | 19
19 | 7 | 6 | 7 | 7 | 7 | 4 | 7 | 6 | 4
13 | 7 | 7 | 7 | 7 | 8 | 22 | 2 | 22 | 8
7 | 4 | 7 | 7 | 4 | 7 | 13 | 7 | 8 | 22
19 | 22 | 7 | 7 | 8 | 21 | 21 | 2 | 8 | 13
6 | 4 | 2 | 19 | 4 | 7 | 4 | 21 | 6 | 21
13 | 8 | 19 | 4 | 7 | 13 | 22 | 7 | 6 | 8
22 | 7 | 6 | 13 | 6 | 4 | 2 | 19 | 21 | 2
13 | 7 | 22 | 7 | 22 | 7 | 6 | 19 | 7 | 13
13 | 13 | 8 | 22 | 7 | 19 | 22 | 2 | 22 | 4
13 | 2 | 13 | 22 | 7 | 21 | 8 | 22 | 7 | 8
4 | 21 | 19 | 8 | 7 | 22 | 8 | 2 | 6 | 2
22 | 8 | 2 | 19 | 6 | 2 | 8 | 6 | 22 | 22
6 | 4 | 2 | 21 | 19 | 19 | 7 | 13 | 4 | 4
22 | 4 | 2 | 19 | 21 | 7 | 22 | 2 | 22 | 7
4 | 13 | 4 | 19 | 2 | 2 | 19 | 22 | 4 | 22
7 | 8 | 19 | 13 | 7 | 4 | 4 | 7 | 13 | 2
7 | 22 | 22 | 19 | 2 | 13 | 2 | 4 | 4 | 2
13 | 2 | 21 | 6 | 13 | 13 | 2 | 2 | 13 | 19
7 | 13 | 4 | 8 | 22 | 19 | 13 | 7 | 13 | 13
4 | 2 | 2 | 19 | 2 | 21 | 21 | 21 | 22 | 8
4 | 22 | 2 | 7 | 2 | 7 | 22 | 7 | 8 | 6
8 | 6 | 13 | 7 | 13 | 8 | 4 | 7 | 13 | 19
8 | 6 | 21 | 8 | 4 | 22 | 22 | 22 | 21 | 2
7 | 4 | 22 | 2 | 13 | 2 | 4 | 6 | 7 | 4
7 | 6 | 8 | 8 | 19 | 4 | 7 | 22 | 4 | 6
2 | 22 | 7 | 2 | 21 | 22 | 22 | 4 | 2 | 7
21 | 7 | 7 | 6 | 21 | 22 | 7 | 19 | 22 | 8
21 | 13 | 2 | 7 | 4 | 7 | 22 | 13 | 6 | 8
2 | 13 | 4 | 21 | 6 | 13 | 22 | 19 | 13 | 7
7 | 4 | 6 | 6 | 7 | 8 | 8 | 19 | 8 | 13
8 | 4 | 2 | 21 | 13 | 6 | 7 | 22 | 22 | 4
8 | 2 | 21 | 19 | 7 | 6 | 7 | 7 | 7 | 22
7 | 13 | 2 | 21 | 7 | 6 | 2 | 21 | 2 | 6
7 | 8 | 8 | 4 | 4 | 7 | 22 | 7 | 7 | 8
13 | 7 | 6 | 7 | 7 | 4 | 22 | 7 | 4 | 21
21 | 19 | 19 | 7 | 19 | 2 | 7 | 19 | 19 | 8
4 | 22 | 2 | 7 | 19 | 2 | 13 | 21 | 21 | 21
2 | 7 | 22 | 4 | 19 | 8 | 13 | 6 | 6 | 2
4 | 4 | 7 | 22 | 19 | 7 | 6 | 8 | 21 | 8
21 | 8 | 8 | 8 | 2 | 13 | 22 | 7 | 4 | 8
22 | 19 | 6 | 7 | 6 | 4 | 2 | 21 | 4 | 6
7 | 7 | 6 | 19 | 7 | 4 | 21 | 21 | 22 | 7
22 | 7 | 6 | 2 | 22 | 6 | 7 | 13 | 8 | 21
2 | 7 | 19 | 6 | 4 | 4 | 7 | 13 | 22 | 6
7 | 13 | 7 | 13 | 13 | 6 | 13 | 4 | 8 | 13
4 | 21 | 8 | 19 | 6 | 4 | 4 | 7 | 7 | 22
4 | 4 | 21 | 21 | 13 | 13 | 7 | 21 | 22 | 8
6 | 4 | 13 | 21 | 21 | 6 | 22 | 6 | 13 | 22
13 | 13 | 6 | 7 | 4 | 8 | 8 | 19 | 2 | 8
7 | 21 | 6 | 8 | 21 | 2 | 6 | 19 | 7 | 21
19 | 6 | 6 | 2 | 7 | 21 | 7 | 21 | 13 | 2
6 | 13 | 2 | 21 | 22 | 13 | 21 | 7 | 6 | 4
19 | 21 | 6 | 4 | 2 | 21 | 19 | 6 | 7 | 13
6 | 7 | 7 | 2 | 2 | 13 | 2 | 21 | 19 | 19
13 | 6 | 7 | 19 | 7 | 7 | 19 | 7 | 7 | 21
13 | 21 | 19 | 6 | 8 | 7 | 22 | 7 | 8 | 6
7 | 19 | 7 | 21 | 4 | 7 | 7 | 6 | 6 | 21
8 | 22 | 4 | 22 | 22 | 13 | 8 | 8 | 13 | 21
7 | 22 | 13 | 21 | 13 | 7 | 22 | 22 | 19 | 7
6 | 7 | 19 | 21 | 7 | 7 | 6 | 7 | 22 | 7
8 | 6 | 2 | 6 | 2 | 7 | 2 | 7 | 6 | 13
4 | 13 | 6 | 19 | 6 | 4 | 6 | 6 | 22 | 8
7 | 22 | 7 | 7 | 7 | 8 | 19 | 4 | 21 | 8
7 | 19 | 8 | 21 | 6 | 7 | 7 | 7 | 2 | 2
19 | 21 | 22 | 8 | 8 | 13 | 2 | 8 | 4 | 6
7 | 13 | 7 | 7 | 7 | 7 | 6 | 21 | 22 | 19
22 | 22 | 13 | 22 | 6 | 19 | 7 | 22 | 13 | 7
8 | 13 | 13 | 22 | 7 | 7 | 8 | 19 | 19 | 19
22 | 8 | 4 | 22 | 6 | 13 | 21 | 4 | 19 | 21
4 | 7 | 4 | 8 | 22 | 7 | 4 | 7 | 6 | 19
2 | 6 | 8 | 2 | 21 | 6 | 4 | 7 | 8 | 7
19 | 22 | 19 | 8 | 13 | 22 | 2 | 2 | 19 | 22
2 | 19 | 7 | 21 | 6 | 21 | 7 | 7 | 8 | 8
7 | 4 | 19 | 7 | 13 | 6 | 4 | 21 | 7 | 13
7 | 13 | 7 | 8 | 2 | 21 | 8 | 7 | 19 | 22
7 | 13 | 19 | 22 | 21 | 13 | 13 | 13 | 7 | 19
2 | 2 | 22 | 8 | 6 | 19 | 22 | 6 | 7 | 19
7 | 7 | 21 | 13 | 7 | 7 | 7 | 7 | 22 | 22
22 | 19 | 7 | 13 | 4 | 19 | 19 | 2 | 22 | 7
7 | 7 | 22 | 4 | 13 | 22 | 6 | 7 | 13 | 6
7 | 8 | 22 | 6 | 7 | 13 | 19 | 21 | 6 | 4
13 | 21 | 4 | 7 | 7 | 8 | 21 | 7 | 8 | 7
6 | 8 | 2 | 7 | 19 | 7 | 13 | 4 | 13 | 4
4 | 21 | 8 | 8 | 7 | 7 | 4 | 19 | 8 | 8
2 | 22 | 4 | 2 | 6 | 8 | 19 | 22 | 2 | 4
19 | 7 | 19 | 4 | 22 | 7 | 7 | 4 | 4 | 22
19 | 6 | 4 | 4 | 8 | 2 | 21 | 7 | 6 | 13
2 | 6 | 7 | 8 | 7 | 21 | 4 | 6 | 8 | 2
19 | 4 | 7 | 22 | 7 | 7 | 6 | 8 | 13 | 7
6 | 19 | 7 | 7 | 13 | 13 | 21 | 21 | 7 | 19
19 | 13 | 6 | 4 | 22 | 21 | 7 | 2 | 7 | 13
13 | 7 | 19 | 13 | 13 | 13 | 8 | 8 | 21 | 7
13 | 2 | 22 | 21 | 19 | 8 | 4 | 2 | 22 | 2
8 | 21 | 7 | 22 | 7 | 21 | 2 | 7 | 6 | 8
4 | 7 | 19 | 7 | 6 | 6 | 13 | 22 | 6 | 22
8 | 8 | 6 | 7 | 13 | 2 | 22 | 13 | 19 | 7
21 | 6 | 7 | 21 | 13 | 6 | 7 | 2 | 7 | 7
2 | 13 | 13 | 8 | 8 | 2 | 8 | 2 | 21 | 22
7 | 2 | 13 | 21 | 7 | 22 | 19 | 8 | 21 | 22
4 | 7 | 22 | 19 | 22 | 4 | 19 | 7 | 19 | 13
21 | 22 | 22 | 4 | 22 | 2 | 19 | 22 | 19 | 19
7 | 8 | 6 | 7 | 19 | 8 | 7 | 7 | 19 | 8
7 | 7 | 13 | 7 | 7 | 2 | 19 | 7 | 19 | 13
19 | 4 | 7 | 13 | 19 | 8 | 7 | 7 | 19 | 4
8 | 7 | 13 | 4 | 21 | 4 | 4 | 4 | 21 | 19
19 | 7 | 22 | 19 | 2 | 2 | 13 | 22 | 7 | 21
22 | 4 | 7 | 13 | 7 | 2 | 7 | 19 | 6 | 13
7 | 2 | 13 | 13 | 6 | 8 | 2 | 7 | 8 | 7
7 | 13 | 13 | 21 | 7 | 22 | 7 | 4 | 4 | 21
22 | 6 | 2 | 7 | 13 | 19 | 7 | 4 | 2 | 6
13 | 21 | 7 | 21 | 8 | 19 | 7 | 7 | 22 | 7
2 | 8 | 4 | 4 | 4 | 8 | 19 | 4 | 7 | 7
4 | 21 | 13 | 7 | 22 | 7 | 19 | 22 | 2 | 7
7 | 8 | 6 | 6 | 7 | 2 | 21 | 7 | 8 | 21
6 | 13 | 21 | 19 | 19 | 7 | 6 | 8 | 7 | 7
8 | 6 | 2 | 22 | 21 | 8 | 8 | 6 | 8 | 4
8 | 13 | 6 | 4 | 6 | 8 | 13 | 4 | 2 | 8
7 | 22 | 2 | 2 | 22 | 19 | 6 | 22 | 2 | 6
13 | 6 | 2 | 22 | 22 | 19 | 21 | 7 | 21 | 4
8 | 7 | 7 | 7 | 2 | 13 | 2 | 6 | 19 | 19
19 | 21 | 6 | 6 | 4 | 19 | 8 | 13 | 13 | 6
13 | 7 | 7 | 8 | 2 | 8 | 21 | 22 | 13 | 7
4 | 22 | 7 | 4 | 21 | 6 | 7 | 7 | 2 | 6
8 | 2 | 6 | 21 | 6 | 2 | 21 | 21 | 2 | 13
13 | 19 | 2 | 19 | 21 | 7 | 21 | 7 | 22 | 7
22 | 13 | 4 | 2 | 19 | 13 | 7 | 7 | 7 | 8
2 | 2 | 2 | 8 | 2 | 8 | 19 | 7 | 13 | 4
4 | 21 | 22 | 7 | 7 | 2 | 21 | 13 | 2 | 13
7 | 2 | 22 | 2 | 22 | 22 | 6 | 22 | 4 | 21
22 | 22 | 13 | 7 | 2 | 21 | 6 | 7 | 7 | 7
19 | 22 | 8 | 4 | 21 | 21 | 8 | 7 | 7 | 13
19 | 8 | 2 | 8 | 7 | 21 | 4 | 4 | 21 | 7
7 | 8 | 19 | 4 | 6 | 8 | 7 | 21 | 13 | 7
7 | 22 | 7 | 19 | 6 | 7 | 4 | 21 | 7 | 19
4 | 22 | 2 | 4 | 6 | 22 | 6 | 19 | 7 | 2
8 | 4 | 19 | 6 | 22 | 7 | 13 | 13 | 7 | 2
7 | 13 | 4 | 19 | 21 | 22 | 7 | 22 | 6 | 7
7 | 13 | 4 | 13 | 21 | 8 | 22 | 7 | 13 | 4
7 | 8 | 22 | 22 | 13 | 6 | 2 | 4 | 6 | 7
7 | 7 | 19 | 13 | 22 | 7 | 2 | 2 | 2 | 6
2 | 6 | 7 | 7 | 6 | 22 | 4 | 7 | 7 | 7
22 | 8 | 13 | 7 | 7 | 6 | 19 | 8 | 21 | 13
13 | 19 | 6 | 7 | 22 | 4 | 2 | 7 | 8 | 13
8 | 19 | 19 | 6 | 2 | 19 | 2 | 6 | 7 | 2
7 | 22 | 7 | 7 | 2 | 22 | 2 | 6 | 19 | 7
7 | 13 | 13 | 8 | 21 | 21 | 13 | 8 | 22 | 8
7 | 7 | 22 | 2 | 13 | 6 | 22 | 13 | 19 | 8
7 | 19 | 19 | 8 | 8 | 7 | 4 | 7 | 6 | 22
2 | 7 | 7 | 7 | 6 | 2 | 7 | 21 | 2 | 19
4 | 6 | 8 | 7 | 4 | 19 | 19 | 6 | 21 | 13
13 | 2 | 4 | 21 | 4 | 19 | 2 | 6 | 7 | 22
8 | 19 | 4 | 7 | 4 | 4 | 22 | 7 | 22 | 19
19 | 13 | 8 | 21 | 8 | 19 | 6 | 7 | 21 | 7
8 | 22 | 2 | 13 | 22 | 19 | 21 | 4 | 2 | 2
8 | 21 | 2 | 7 | 6 | 21 | 8 | 2 | 7 | 21
22 | 8 | 8 | 7 | 13 | 21 | 19 | 22 | 4 | 22
13 | 22 | 7 | 6 | 6 | 21 | 7 | 21 | 21 | 7
7 | 8 | 21 | 7 | 6 | 19 | 7 | 21 | 22 | 19
4 | 8 | 22 | 7 | 8 | 22 | 4 | 7 | 2 | 13
13 | 8 | 19 | 4 | 21 | 7 | 7 | 21 | 21 | 8
21 | 22 | 21 | 21 | 19 | 7 | 22 | 8 | 13 | 19
21 | 8 | 19 | 6 | 2 | 22 | 4 | 13 | 4 | 8
19 | 8 | 7 | 21 | 21 | 19 | 19 | 4 | 7 | 8
4 | 6 | 13 | 13 | 2 | 8 | 22 | 7 | 19 | 6
19 | 7 | 2 | 22 | 22 | 13 | 21 | 7 | 7 | 2
2 | 7 | 22 | 19 | 21 | 2 | 7 | 8 | 6 | 4
6 | 19 | 19 | 19 | 8 | 8 | 8 | 22 | 7 | 2
8 | 13 | 7 | 22 | 21 | 4 | 7 | 4 | 19 | 19
4 | 2 | 22 | 8 | 13 | 4 | 19 | 7 | 22 | 19
4 | 6 | 19 | 19 | 2 | 6 | 22 | 21 | 21 | 2
7 | 22 | 7 | 8 | 22 | 22 | 6 | 6 | 7 | 22
13 | 2 | 7 | 22 | 7 | 22 | 4 | 8 | 7 | 6
6 | 19 | 13 | 13 | 7 | 13 | 21 | 22 | 6 | 4
8 | 22 | 6 | 8 | 4 | 8 | 19 | 13 | 13 | 22
6 | 7 | 21 | 4 | 4 | 8 | 7 | 7 | 7 | 2
2 | 13 | 4 | 4 | 21 | 8 | 22 | 22 | 13 | 21
2 | 4 | 6 | 22 | 7 | 8 | 6 | 13 | 4 | 7
13 | 8 | 7 | 13 | 6 | 8 | 4 | 19 | 13 | 6
21 | 7 | 22 | 22 | 8 | 7 | 22 | 8 | 13 | 19
6 | 2 | 4 | 2 | 22 | 8 | 6 | 13 | 13 | 21
2 | 13 | 21 | 6 | 2 | 13 | 7 | 2 | 19 | 7
22 | 22 | 6 | 19 | 7 | 7 | 13 | 7 | 7 | 2
6 | 4 | 7 | 22 | 8 | 2 | 22 | 13 | 22 | 2
8 | 7 | 21 | 4 | 6 | 8 | 8 | 2 | 6 | 13
4 | 8 | 21 | 2 | 7 | 22 | 22 | 8 | 13 | 13
2 | 8 | 4 | 13 | 2 | 7 | 13 | 2 | 13 | 13
8 | 6 | 4 | 21 | 2 | 19 | 8 | 7 | 13 | 22
4 | 22 | 7 | 4 | 7 | 7 | 21 | 2 | 6 | 6
2 | 7 | 13 | 19 | 6 | 2 | 6 | 22 | 19 | 4
6 | 7 | 19 | 7 | 21 | 8 | 7 | 7 | 4 | 13
7 | 19 | 7 | 21 | 4 | 22 | 22 | 7 | 7 | 21
22 | 7 | 8 | 8 | 7 | 8 | 22 | 13 | 22 | 7
7 | 4 | 19 | 19 | 4 | 4 | 7 | 7 | 13 | 7
8 | 22 | 13 | 6 | 7 | 8 | 2 | 6 | 7 | 7
7 | 13 | 6 | 7 | 22 | 4 | 2 | 7 | 22 | 6
22 | 13 | 21 | 6 | 2 | 6 | 2 | 8 | 6 | 7
6 | 7 | 8 | 22 | 22 | 8 | 22 | 8 | 21 | 21
7 | 6 | 6 | 2 | 8 | 13 | 4 | 7 | 6 | 19
22 | 7 | 6 | 6 | 7 | 4 | 2 | 4 | 21 | 7
19 | 21 | 19 | 2 | 7 | 13 | 6 | 21 | 7 | 6
6 | 13 | 13 | 4 | 22 | 6 | 7 | 6 | 2 | 22
4 | 8 | 22 | 7 | 8 | 7 | 8 | 7 | 7 | 7
19 | 21 | 22 | 22 | 7 | 8 | 6 | 13 | 7 | 6
7 | 13 | 7 | 4 | 13 | 22 | 13 | 7 | 2 | 2
13 | 7 | 19 | 7 | 8 | 2 | 22 | 8 | 22 | 4
7 | 22 | 2 | 7 | 8 | 7 | 6 | 7 | 13 | 4
19 | 19 | 21 | 2 | 7 | 6 | 21 | 6 | 2 | 13
21 | 8 | 7 | 8 | 6 | 21 | 22 | 19 | 13 | 2
7 | 6 | 7 | 13 | 7 | 21 | 8 | 8 | 19 | 22
4 | 4 | 7 | 8 | 4 | 7 | 13 | 21 | 7 | 8
4 | 7 | 21 | 4 | 13 | 7 | 7 | 19 | 4 | 7
22 | 19 | 7 | 2 | 2 | 4 | 2 | 7 | 7 | 2
7 | 4 | 8 | 13 | 6 | 7 | 13 | 21 | 2 | 7
2 | 19 | 2 | 8 | 8 | 13 | 19 | 22 | 7 | 21
8 | 4 | 13 | 8 | 4 | 4 | 6 | 7 | 7 | 7
19 | 4 | 6 | 22 | 22 | 2 | 7 | 22 | 7 | 2
8 | 2 | 2 | 22 | 21 | 6 | 22 | 21 | 13 | 7
13 | 4 | 7 | 7 | 7 | 2 | 2 | 13 | 7 | 22
21 | 6 | 19 | 8 | 4 | 7 | 2 | 8 | 19 | 2
19 | 21 | 7 | 7 | 21 | 8 | 13 | 22 | 13 | 19
22 | 13 | 4 | 19 | 7 | 7 | 21 | 7 | 7 | 6
21 | 13 | 21 | 7 | 22 | 7 | 2 | 6 | 22 | 6
21 | 7 | 21 | 2 | 21 | 7 | 2 | 4 | 13 | 7
13 | 21 | 21 | 7 | 7 | 8 | 7 | 22 | 7 | 21
6 | 19 | 2 | 4 | 21 | 7 | 4 | 7 | 8 | 7
8 | 6 | 8 | 7 | 19 | 6 | 22 | 21 | 7 | 21
7 | 8 | 8 | 19 | 2 | 19 | 13 | 13 | 19 | 19
21 | 13 | 7 | 13 | 22 | 13 | 19 | 13 | 21 | 4
4 | 21 | 4 | 4 | 21 | 22 | 8 | 4 | 7 | 4
21 | 6 | 7 | 4 | 19 | 22 | 6 | 22 | 2 | 8
8 | 7 | 6 | 7 | 7 | 21 | 13 | 19 | 8 | 2
6 | 2 | 7 | 22 | 7 | 21 | 2 | 19 | 4 | 8
4 | 7 | 2 | 2 | 8 | 22 | 8 | 7 | 19 | 22
19 | 19 | 7 | 8 | 7 | 22 | 6 | 8 | 7 | 21
13 | 7 | 2 | 8 | 8 | 4 | 19 | 8 | 6 | 6
7 | 21 | 4 | 2 | 21 | 2 | 4 | 6 | 13 | 6
7 | 8 | 22 | 2 | 22 | 7 | 21 | 6 | 21 | 19
22 | 13 | 4 | 6 | 8 | 6 | 7 | 19 | 8 | 6
7 | 22 | 21 | 13 | 6 | 2 | 21 | 7 | 2 | 21
2 | 2 | 21 | 7 | 6 | 21 | 4 | 7 | 22 | 13
13 | 19 | 8 | 13 | 13 | 7 | 6 | 7 | 19 | 8
4 | 19 | 19 | 21 | 7 | 19 | 7 | 13 | 19 | 19
13 | 19 | 13 | 22 | 7 | 13 | 13 | 7 | 4 | 22
19 | 8 | 7 | 2 | 21 | 13 | 6 | 21 | 2 | 4
13 | 6 | 7 | 4 | 2 | 4 | 2 | 4 | 4 | 13
7 | 7 | 13 | 7 | 8 | 6 | 13 | 22 | 21 | 22
7 | 22 | 8 | 6 | 2 | 19 | 4 | 2 | 21 | 8
2 | 7 | 6 | 13 | 7 | 7 | 4 | 22 | 7 | 21
2 | 7 | 7 | 19 | 7 | 6 | 6 | 6 | 21 | 6
8 | 7 | 2 | 7 | 4 | 7 | 13 | 2 | 13 | 7
21 | 7 | 7 | 22 | 19 | 19 | 2 | 6 | 2 | 7
2 | 8 | 21 | 2 | 8 | 8 | 6 | 8 | 8 | 7
2 | 22 | 22 | 4 | 19 | 13 | 7 | 19 | 6 | 22
4 | 7 | 6 | 7 | 7 | 19 | 22 | 22 | 19 | 21
19 | 8 | 19 | 2 | 22 | 13 | 13 | 22 | 4 | 8
21 | 21 | 4 | 6 | 13 | 2 | 6 | 2 | 22 | 6
7 | 4 | 13 | 7 | 7 | 7 | 21 | 8 | 22 | 6
19 | 19 | 7 | 22 | 19 | 7 | 19 | 8 | 19 | 7
22 | 2 | 13 | 13 | 4 | 22 | 6 | 2 | 6 | 8
4 | 21 | 21 | 7 | 8 | 21 | 6 | 21 | 19 | 21
7 | 19 | 22 | 8 | 21 | 6 | 6 | 7 | 7 | 19
7 | 13 | 7 | 2 | 6 | 13 | 19 | 8 | 2 | 8
8 | 7 | 7 | 4 | 7 | 8 | 13 | 8 | 7 | 7
6 | 7 | 7 | 8 | 13 | 13 | 22 | 2 | 2 | 2
13 | 7 | 13 | 7 | 2 | 22 | 7 | 8 | 4 | 6
6 | 8 | 8 | 7 | 19 | 6 | 4 | 2 | 19 | 7
7 | 7 | 7 | 21 | 6 | 7 | 4 | 4 | 6 | 2
19 | 8 | 19 | 7 | 6 | 21 | 8 | 7 | 4 | 19
19 | 7 | 13 | 8 | 4 | 6 | 4 | 22 | 2 | 8
6 | 13 | 2 | 19 | 6 | 2 | 7 | 22 | 7 | 19
6 | 6 | 7 | 6 | 8 | 7 | 13 | 19 | 7 | 8
6 | 2 | 2 | 8 | 21 | 22 | 4 | 7 | 13 | 2
19 | 7 | 8 | 19 | 2 | 4 | 4 | 21 | 7 | 21
7 | 21 | 2 | 19 | 4 | 7 | 13 | 21 | 19 | 4
7 | 8 | 8 | 7 | 6 | 4 | 19 | 6 | 7 | 21
6 | 19 | 22 | 6 | 7 | 19 | 19 | 21 | 7 | 7
22 | 7 | 4 | 22 | 7 | 8 | 7 | 19 | 21 | 4
7 | 21 | 21 | 22 | 2 | 2 | 6 | 22 | 6 | 2
22 | 2 | 7 | 21 | 4 | 2 | 13 | 13 | 8 | 7
7 | 7 | 2 | 8 | 4 | 2 | 21 | 2 | 22 | 8
7 | 13 | 4 | 21 | 19 | 13 | 7 | 22 | 8 | 21
6 | 19 | 21 | 8 | 2 | 6 | 19 | 21 | 6 | 4
7 | 19 | 22 | 7 | 8 | 2 | 22 | 7 | 22 | 21
21 | 2 | 7 | 13 | 6 | 4 | 19 | 2 | 6 | 7
19 | 7 | 21 | 13 | 19 | 6 | 22 | 19 | 2 | 22
7 | 19 | 2 | 2 | 19 | 21 | 22 | 7 | 4 | 7
7 | 13 | 7 | 21 | 6 | 21 | 4 | 8 | 2 | 8
8 | 22 | 13 | 13 | 7 | 7 | 2 | 21 | 19 | 8
7 | 19 | 13 | 7 | 4 | 21 | 19 | 8 | 21 | 8
8 | 19 | 7 | 8 | 19 | 13 | 22 | 7 | 8 | 2
21 | 22 | 21 | 21 | 19 | 21 | 7 | 21 | 7 | 8
2 | 22 | 6 | 7 | 7 | 4 | 7 | 8 | 6 | 7
4 | 6 | 4 | 4 | 21 | 22 | 2 | 7 | 19 | 22
4 | 21 | 7 | 21 | 2 | 7 | 22 | 2 | 4 | 4
7 | 2 | 19 | 19 | 2 | 21 | 7 | 22 | 4 | 8
7 | 19 | 22 | 6 | 2 | 7 | 22 | 13 | 8 | 6
8 | 19 | 19 | 7 | 13 | 19 | 22 | 7 | 8 | 7
6 | 7 | 19 | 2 | 19 | 22 | 8 | 21 | 6 | 6
13 | 7 | 21 | 13 | 19 | 22 | 22 | 7 | 7 | 4
7 | 19 | 4 | 22 | 6 | 7 | 4 | 21 | 7 | 2
13 | 19 | 13 | 22 | 7 | 13 | 6 | 21 | 22 | 8
22 | 8 | 6 | 19 | 6 | 22 | 7 | 13 | 8 | 19
7 | 6 | 6 | 22 | 7 | 7 | 7 | 21 | 19 | 21
13 | 8 | 6 | 22 | 2 | 22 | 8 | 19 | 22 | 4
2 | 7 | 21 | 7 | 8 | 6 | 19 | 7 | 19 | 2
7 | 21 | 6 | 4 | 6 | 7 | 6 | 6 | 7 | 19
22 | 22 | 19 | 7 | 6 | 8 | 19 | 7 | 8 | 19
19 | 22 | 21 | 7 | 2 | 13 | 2 | 21 | 22 | 8
8 | 19 | 4 | 7 | 2 | 6 | 2 | 2 | 13 | 2
19 | 7 | 4 | 21 | 21 | 13 | 13 | 8 | 19 | 2
13 | 19 | 4 | 13 | 4 | 4 | 19 | 21 | 13 | 6
4 | 2 | 7 | 13 | 8 | 21 | 19 | 4 | 19 | 7
22 | 22 | 21 | 6 | 7 | 7 | 21 | 19 | 6 | 6
13 | 8 | 2 | 7 | 22 | 6 | 7 | 13 | 8 | 21
4 | 8 | 6 | 6 | 8 | 22 | 7 | 21 | 19 | 21
7 | 19 | 19 | 21 | 7 | 13 | 4 | 4 | 7 | 6
7 | 8 | 7 | 7 | 2 | 21 | 6 | 8 | 4 | 4
13 | 4 | 6 | 8 | 21 | 7 | 13 | 8 | 21 | 7
4 | 21 | 4 | 7 | 4 | 6 | 8 | 7 | 22 | 19
8 | 21 | 7 | 21 | 21 | 4 | 22 | 22 | 8 | 22
21 | 19 | 19 | 19 | 8 | 21 | 13 | 7 | 7 | 8
22 | 4 | 7 | 4 | 7 | 7 | 4 | 19 | 7 | 6
8 | 13 | 22 | 6 | 13 | 22 | 8 | 13 | 6 | 21
19 | 22 | 8 | 2 | 4 | 7 | 19 | 7 | 13 | 13
21 | 2 | 8 | 21 | 13 | 8 | 8 | 13 | 7 | 4
4 | 2 | 22 | 13 | 13 | 2 | 7 | 7 | 7 | 6
19 | 4 | 7 | 2 | 8 | 8 | 4 | 19 | 19 | 19
19 | 4 | 13 | 7 | 2 | 2 | 13 | 21 | 2 | 4
6 | 22 | 8 | 7 | 13 | 2 | 21 | 7 | 4 | 2
7 | 7 | 19 | 19 | 6 | 4 | 19 | 21 | 19 | 22
4 | 21 | 6 | 6 | 4 | 8 | 7 | 2 | 13 | 4
4 | 22 | 6 | 8 | 6 | 19 | 4 | 22 | 22 | 21
7 | 7 | 6 | 22 | 6 | 7 | 8 | 19 | 8 | 7
4 | 2 | 6 | 7 | 4 | 4 | 13 | 2 | 2 | 8
4 | 7 | 8 | 13 | 22 | 2 | 7 | 19 | 19 | 21
7 | 7 | 13 | 2 | 8 | 19 | 4 | 2 | 4 | 2
22 | 2 | 22 | 7 | 13 | 6 | 21 | 8 | 4 | 7
2 | 6 | 6 | 13 | 19 | 21 | 7 | 7 | 22 | 19
4 | 13 | 21 | 2 | 8 | 21 | 22 | 2 | 19 | 7
2 | 22 | 7 | 7 | 6 | 8 | 7 | 7 | 22 | 21
6 | 7 | 7 | 8 | 21 | 22 | 4 | 2 | 21 | 2
22 | 7 | 21 | 7 | 2 | 22 | 4 | 8 | 7 | 21
8 | 6 | 4 | 6 | 7 | 2 | 21 | 13 | 7 | 4
13 | 7 | 4 | 7 | 4 | 7 | 2 | 7 | 4 | 8
7 | 19 | 2 | 19 | 7 | 2 | 4 | 6 | 7 | 2
6 | 21 | 6 | 2 | 13 | 6 | 8 | 6 | 19 | 21
13 | 2 | 2 | 7 | 8 | 13 | 6 | 6 | 8 | 6
7 | 21 | 22 | 7 | 2 | 7 | 7 | 8 | 7 | 6
22 | 7 | 22 | 21 | 21 | 2 | 6 | 4 | 7 | 8
2 | 7 | 22 | 21 | 6 | 7 | 13 | 21 | 7 | 6
22 | 8 | 13 | 2 | 7 | 6 | 7 | 21 | 22 | 2
8 | 7 | 2 | 7 | 4 | 7 | 21 | 6 | 7 | 21
22 | 8 | 4 | 6 | 4 | 22 | 7 | 7 | 6 | 8
6 | 8 | 4 | 22 | 21 | 8 | 7 | 6 | 6 | 21
21 | 4 | 13 | 7 | 21 | 2 | 13 | 22 | 8 | 8
13 | 21 | 21 | 8 | 19 | 19 | 2 | 21 | 13 | 8
22 | 19 | 13 | 4 | 8 | 19 | 19 | 6 | 7 | 19
7 | 4 | 6 | 7 | 8 | 19 | 2 | 22 | 13 | 22
6 | 22 | 19 | 7 | 2 | 13 | 2 | 8 | 6 | 19
8 | 22 | 13 | 8 | 21 | 8 | 19 | 8 | 6 | 22
19 | 2 | 19 | 2 | 22 | 7 | 19 | 4 | 2 | 13
21 | 2 | 13 | 6 | 4 | 19 | 19 | 21 | 19 | 21
19 | 4 | 7 | 21 | 6 | 21 | 19 | 4 | 22 | 8
7 | 6 | 22 | 7 | 6 | 21 | 6 | 19 | 22 | 7
22 | 7 | 22 | 21 | 21 | 21 | 6 | 7 | 19 | 4
6 | 6 | 19 | 22 | 7 | 8 | 22 | 7 | 22 | 21
8 | 13 | 6 | 13 | 13 | 6 | 7 | 19 | 8 | 6
21 | 21 | 19 | 4 | 7 | 21 | 21 | 7 | 2 | 6
19 | 7 | 8 | 2 | 21 | 13 | 7 | 21 | 2 | 4
8 | 21 | 2 | 8 | 22 | 7 | 22 | 7 | 13 | 22
19 | 19 | 19 | 21 | 22 | 13 | 19 | 7 | 19 | 2
13 | 2 | 19 | 22 | 19 | 21 | 21 | 6 | 2 | 7
19 | 19 | 7 | 13 | 2 | 13 | 19 | 2 | 6 | 13
22 | 2 | 7 | 8 | 2 | 6 | 4 | 13 | 13 | 7
4 | 21 | 6 | 21 | 19 | 4 | 7 | 19 | 22 | 19
2 | 13 | 2 | 21 | 22 | 7 | 7 | 22 | 7 | 22
8 | 22 | 7 | 8 | 22 | 2 | 22 | 6 | 21 | 21
13 | 7 | 22 | 7 | 13 | 7 | 8 | 19 | 13 | 7
7 | 7 | 19 | 19 | 7 | 8 | 7 | 7 | 2 | 13
7 | 13 | 4 | 8 | 2 | 7 | 8 | 6 | 6 | 21
7 | 13 | 21 | 4 | 8 | 22 | 6 | 6 | 13 | 13
7 | 13 | 7 | 7 | 19 | 7 | 7 | 13 | 7 | 7
13 | 4 | 2 | 13 | 7 | 13 | 22 | 8 | 7 | 2
19 | 13 | 6 | 7 | 21 | 4 | 8 | 21 | 7 | 21
21 | 13 | 8 | 4 | 22 | 13 | 7 | 4 | 21 | 19
21 | 4 | 13 | 22 | 8 | 21 | 6 | 7 | 21 | 8
13 | 8 | 21 | 6 | 19 | 6 | 8 | 8 | 13 | 4
22 | 7 | 22 | 13 | 19 | 22 | 6 | 2 | 13 | 6
8 | 6 | 19 | 19 | 21 | 19 | 2 | 4 | 19 | 21
13 | 6 | 4 | 6 | 13 | 22 | 22 | 21 | 8 | 13
7 | 22 | 6 | 7 | 13 | 4 | 6 | 13 | 22 | 13
6 | 22 | 7 | 21 | 21 | 21 | 6 | 2 | 7 | 7
7 | 22 | 21 | 7 | 19 | 4 | 2 | 7 | 21 | 8
22 | 7 | 22 | 6 | 2 | 7 | 6 | 7 | 19 | 8
22 | 4 | 21 | 2 | 7 | 4 | 22 | 4 | 7 | 7
8 | 2 | 4 | 2 | 7 | 21 | 8 | 8 | 6 | 7
2 | 7 | 13 | 21 | 4 | 22 | 21 | 7 | 13 | 13
8 | 13 | 2 | 7 | 21 | 7 | 8 | 8 | 7 | 21
21 | 19 | 2 | 21 | 21 | 6 | 4 | 4 | 22 | 22
13 | 21 | 2 | 22 | 21 | 19 | 6 | 6 | 7 | 21
22 | 19 | 22 | 13 | 7 | 2 | 8 | 4 | 21 | 21
13 | 4 | 6 | 7 | 13 | 19 | 22 | 4 | 13 | 7
7 | 13 | 21 | 19 | 8 | 2 | 21 | 19 | 2 | 2
6 | 7 | 4 | 4 | 8 | 7 | 21 | 21 | 19 | 13
6 | 7 | 22 | 22 | 4 | 7 | 22 | 19 | 21 | 4
22 | 4 | 6 | 6 | 19 | 13 | 7 | 6 | 19 | 6
21 | 7 | 6 | 19 | 7 | 19 | 22 | 22 | 13 | 6
21 | 7 | 6 | 8 | 13 | 21 | 8 | 7 | 7 | 6
7 | 19 | 13 | 8 | 21 | 7 | 4 | 8 | 2 | 7
7 | 4 | 19 | 7 | 7 | 2 | 6 | 2 | 7 | 19
13 | 21 | 13 | 6 | 2 | 22 | 22 | 2 | 8 | 2
19 | 4 | 21 | 19 | 6 | 6 | 19 | 8 | 7 | 21
19 | 22 | 22 | 19 | 6 | 21 | 7 | 8 | 19 | 6
6 | 7 | 8 | 2 | 2 | 22 | 19 | 7 | 6 | 7
6 | 21 | 22 | 4 | 2 | 22 | 19 | 21 | 13 | 21
7 | 7 | 19 | 2 | 4 | 7 | 22 | 22 | 2 | 13
19 | 22 | 7 | 4 | 7 | 6 | 7 | 22 | 7 | 7
6 | 2 | 2 | 2 | 6 | 8 | 13 | 6 | 21 | 21
19 | 8 | 13 | 8 | 2 | 6 | 8 | 6 | 2 | 13
2 | 7 | 7 | 21 | 19 | 13 | 4 | 8 | 6 | 22
22 | 19 | 19 | 21 | 21 | 8 | 22 | 13 | 7 | 21
4 | 21 | 7 | 19 | 7 | 19 | 7 | 19 | 19 | 2
6 | 7 | 7 | 4 | 2 | 6 | 8 | 2 | 2 | 21
21 | 13 | 21 | 6 | 13 | 7 | 22 | 6 | 6 | 2
7 | 21 | 4 | 21 | 8 | 6 | 8 | 2 | 22 | 13
7 | 4 | 13 | 19 | 6 | 7 | 4 | 4 | 21 | 6
22 | 7 | 7 | 4 | 8 | 7 | 4 | 7 | 2 | 21
21 | 4 | 21 | 6 | 13 | 22 | 19 | 19 | 13 | 13
21 | 7 | 21 | 7 | 21 | 2 | 7 | 6 | 21 | 6
19 | 6 | 7 | 22 | 7 | 2 | 6 | 2 | 13 | 22
21 | 8 | 7 | 21 | 2 | 4 | 6 | 4 | 22 | 7
21 | 7 | 8 | 6 | 7 | 19 | 6 | 22 | 4 | 2
7 | 7 | 6 | 21 | 8 | 7 | 19 | 13 | 19 | 19
4 | 4 | 4 | 19 | 7 | 4 | 22 | 4 | 2 | 22
13 | 21 | 13 | 2 | 19 | 4 | 19 | 7 | 7 | 19
7 | 7 | 8 | 21 | 2 | 21 | 2 | 21 | 7 | 7
21 | 19 | 7 | 4 | 22 | 8 | 7 | 7 | 4 | 21
4 | 22 | 2 | 22 | 4 | 7 | 7 | 6 | 6 | 13
22 | 8 | 13 | 6 | 8 | 4 | 21 | 4 | 19 | 4
13 | 8 | 7 | 22 | 22 | 21 | 22 | 6 | 7 | 13
21 | 7 | 22 | 22 | 8 | 6 | 21 | 8 | 6 | 21
8 | 19 | 13 | 8 | 8 | 13 | 6 | 8 | 7 | 8
19 | 4 | 13 | 2 | 6 | 19 | 22 | 7 | 2 | 8
7 | 13 | 22 | 2 | 13 | 22 | 13 | 13 | 7 | 21
8 | 19 | 6 | 21 | 6 | 19 | 13 | 2 | 8 | 13
7 | 8 | 19 | 2 | 4 | 7 | 8 | 6 | 4 | 2
7 | 8 | 2 | 6 | 21 | 13 | 22 | 13 | 19 | 2
22 | 7 | 19 | 7 | 21 | 2 | 8 | 8 | 7 | 22
13 | 22 | 7 | 21 | 6 | 22 | 21 | 21 | 6 | 7
8 | 4 | 13 | 4 | 13 | 6 | 6 | 2 | 4 | 19

## 3. Perform
# Stories/Backlog Items: | 15
Simulated Project | Avg. Cycle Time | Project Length | Cumulative
Project #1 | 11.5 | 172.5 | 0.001
Project #2 | 11.2 | 168 | 0.001
Project #3 | 11.8 | 177 | 0.001
Project #4 | 12.6 | 189 | 0.001
Project #5 | 10.5 | 157.5 | 0.001
Project #6 | 13.5 | 202.5 | 0.001
Project #7 | 10.1 | 151.5 | 0.001
Project #8 | 12.7 | 190.5 | 0.001
Project #9 | 11.1 | 166.5 | 0.001
Project #10 | 12 | 180 | 0.001
Project #11 | 7.5 | 112.5 | 0.001
Project #12 | 11 | 165 | 0.001
Project #13 | 7.3 | 109.5 | 0.001
Project #14 | 12.1 | 181.5 | 0.001
Project #15 | 13.7 | 205.5 | 0.001
Project #16 | 13.5 | 202.5 | 0.001
Project #17 | 12.5 | 187.5 | 0.001
Project #18 | 11.2 | 168 | 0.001
Project #19 | 13.1 | 196.5 | 0.001
Project #20 | 13 | 195 | 0.001
Project #21 | 10.6 | 159 | 0.001
Project #22 | 13 | 195 | 0.001
Project #23 | 11.1 | 166.5 | 0.001
Project #24 | 9.1 | 136.5 | 0.001
Project #25 | 11.3 | 169.5 | 0.001
Project #26 | 10.8 | 162 | 0.001
Project #27 | 8.7 | 130.5 | 0.001
Project #28 | 11.2 | 168 | 0.001
Project #29 | 12.2 | 183 | 0.001
Project #30 | 10.6 | 159 | 0.001
Project #31 | 10.3 | 154.5 | 0.001
Project #32 | 13.8 | 207 | 0.001
Project #33 | 14.8 | 222 | 0.001
Project #34 | 12.2 | 183 | 0.001
Project #35 | 13.2 | 198 | 0.001
Project #36 | 8.7 | 130.5 | 0.001
Project #37 | 9.9 | 148.5 | 0.001
Project #38 | 10.6 | 159 | 0.001
Project #39 | 11.8 | 177 | 0.001
Project #40 | 9.7 | 145.5 | 0.001
Project #41 | 10.6 | 159 | 0.001
Project #42 | 8.1 | 121.5 | 0.001
Project #43 | 8.6 | 129 | 0.001
Project #44 | 14.5 | 217.5 | 0.001
Project #45 | 15.4 | 231 | 0.001
Project #46 | 15.1 | 226.5 | 0.001
Project #47 | 9.6 | 144 | 0.001
Project #48 | 14.2 | 213 | 0.001
Project #49 | 14.8 | 222 | 0.001
Project #50 | 8 | 120 | 0.001
Project #51 | 12.3 | 184.5 | 0.001
Project #52 | 9.6 | 144 | 0.001
Project #53 | 11.8 | 177 | 0.001
Project #54 | 10.7 | 160.5 | 0.001
Project #55 | 12 | 180 | 0.001
Project #56 | 11.5 | 172.5 | 0.001
Project #57 | 7.5 | 112.5 | 0.001
Project #58 | 14.8 | 222 | 0.001
Project #59 | 12.9 | 193.5 | 0.001
Project #60 | 11.7 | 175.5 | 0.001
Project #61 | 7 | 105 | 0.001
Project #62 | 9.5 | 142.5 | 0.001
Project #63 | 10.5 | 157.5 | 0.001
Project #64 | 9.2 | 138 | 0.001
Project #65 | 13.2 | 198 | 0.001
Project #66 | 12.3 | 184.5 | 0.001
Project #67 | 13.4 | 201 | 0.001
Project #68 | 8.6 | 129 | 0.001
Project #69 | 13 | 195 | 0.001
Project #70 | 15.3 | 229.5 | 0.001
Project #71 | 12.4 | 186 | 0.001
Project #72 | 10.2 | 153 | 0.001
Project #73 | 10.2 | 153 | 0.001
Project #74 | 10.5 | 157.5 | 0.001
Project #75 | 13.6 | 204 | 0.001
Project #76 | 10.3 | 154.5 | 0.001
Project #77 | 13.4 | 201 | 0.001
Project #78 | 12 | 180 | 0.001
Project #79 | 12 | 180 | 0.001
Project #80 | 11.1 | 166.5 | 0.001
Project #81 | 7.6 | 114 | 0.001
Project #82 | 7.9 | 118.5 | 0.001
Project #83 | 7 | 105 | 0.001
Project #84 | 13.4 | 201 | 0.001
Project #85 | 10.1 | 151.5 | 0.001
Project #86 | 7.6 | 114 | 0.001
Project #87 | 9.8 | 147 | 0.001
Project #88 | 10.9 | 163.5 | 0.001
Project #89 | 9.6 | 144 | 0.001
Project #90 | 6.8 | 102 | 0.001
Project #91 | 12.3 | 184.5 | 0.001
Project #92 | 9.8 | 147 | 0.001
Project #93 | 9.3 | 139.5 | 0.001
Project #94 | 11 | 165 | 0.001
Project #95 | 7.1 | 106.5 | 0.001
Project #96 | 9.1 | 136.5 | 0.001
Project #97 | 12.2 | 183 | 0.001
Project #98 | 6.5 | 97.5 | 0.001
Project #99 | 13.5 | 202.5 | 0.001
Project #100 | 15.3 | 229.5 | 0.001
Project #101 | 12.2 | 183 | 0.001
Project #102 | 14.4 | 216 | 0.001
Project #103 | 12.7 | 190.5 | 0.001
Project #104 | 12.1 | 181.5 | 0.001
Project #105 | 14.5 | 217.5 | 0.001
Project #106 | 12.6 | 189 | 0.001
Project #107 | 11.9 | 178.5 | 0.001
Project #108 | 10.9 | 163.5 | 0.001
Project #109 | 8.4 | 126 | 0.001
Project #110 | 8.1 | 121.5 | 0.001
Project #111 | 8.6 | 129 | 0.001
Project #112 | 8.4 | 126 | 0.001
Project #113 | 11.3 | 169.5 | 0.001
Project #114 | 11.9 | 178.5 | 0.001
Project #115 | 10.8 | 162 | 0.001
Project #116 | 10.5 | 157.5 | 0.001
Project #117 | 9.4 | 141 | 0.001
Project #118 | 12 | 180 | 0.001
Project #119 | 13.9 | 208.5 | 0.001
Project #120 | 12.3 | 184.5 | 0.001
Project #121 | 8.7 | 130.5 | 0.001
Project #122 | 10.7 | 160.5 | 0.001
Project #123 | 9 | 135 | 0.001
Project #124 | 8.8 | 132 | 0.001
Project #125 | 14.6 | 219 | 0.001
Project #126 | 9.1 | 136.5 | 0.001
Project #127 | 9 | 135 | 0.001
Project #128 | 14.7 | 220.5 | 0.001
Project #129 | 7.8 | 117 | 0.001
Project #130 | 13 | 195 | 0.001
Project #131 | 11.2 | 168 | 0.001
Project #132 | 13.9 | 208.5 | 0.001
Project #133 | 12.1 | 181.5 | 0.001
Project #134 | 11.3 | 169.5 | 0.001
Project #135 | 11.4 | 171 | 0.001
Project #136 | 10.3 | 154.5 | 0.001
Project #137 | 15.3 | 229.5 | 0.001
Project #138 | 9.5 | 142.5 | 0.001
Project #139 | 9.6 | 144 | 0.001
Project #140 | 10.9 | 163.5 | 0.001
Project #141 | 8.8 | 132 | 0.001
Project #142 | 10.3 | 154.5 | 0.001
Project #143 | 11.7 | 175.5 | 0.001
Project #144 | 8.7 | 130.5 | 0.001
Project #145 | 11.7 | 175.5 | 0.001
Project #146 | 7.6 | 114 | 0.001
Project #147 | 9 | 135 | 0.001
Project #148 | 12 | 180 | 0.001
Project #149 | 8.3 | 124.5 | 0.001
Project #150 | 12.1 | 181.5 | 0.001
Project #151 | 14.4 | 216 | 0.001
Project #152 | 10.4 | 156 | 0.001
Project #153 | 10.4 | 156 | 0.001
Project #154 | 12.9 | 193.5 | 0.001
Project #155 | 12.1 | 181.5 | 0.001
Project #156 | 13.9 | 208.5 | 0.001
Project #157 | 9 | 135 | 0.001
Project #158 | 15.5 | 232.5 | 0.001
Project #159 | 12.3 | 184.5 | 0.001
Project #160 | 7.6 | 114 | 0.001
Project #161 | 7 | 105 | 0.001
Project #162 | 12.9 | 193.5 | 0.001
Project #163 | 12.3 | 184.5 | 0.001
Project #164 | 14.2 | 213 | 0.001
Project #165 | 11.2 | 168 | 0.001
Project #166 | 11.8 | 177 | 0.001
Project #167 | 12.3 | 184.5 | 0.001
Project #168 | 13.9 | 208.5 | 0.001
Project #169 | 15.2 | 228 | 0.001
Project #170 | 5.8 | 87 | 0.001
Project #171 | 11.7 | 175.5 | 0.001
Project #172 | 12.3 | 184.5 | 0.001
Project #173 | 15.4 | 231 | 0.001
Project #174 | 12.6 | 189 | 0.001
Project #175 | 12.6 | 189 | 0.001
Project #176 | 14.5 | 217.5 | 0.001
Project #177 | 9.6 | 144 | 0.001
Project #178 | 11.5 | 172.5 | 0.001
Project #179 | 11.1 | 166.5 | 0.001
Project #180 | 12.1 | 181.5 | 0.001
Project #181 | 12.3 | 184.5 | 0.001
Project #182 | 14.2 | 213 | 0.001
Project #183 | 10.8 | 162 | 0.001
Project #184 | 14.2 | 213 | 0.001
Project #185 | 13.8 | 207 | 0.001
Project #186 | 9.2 | 138 | 0.001
Project #187 | 10.3 | 154.5 | 0.001
Project #188 | 11.8 | 177 | 0.001
Project #189 | 12.4 | 186 | 0.001
Project #190 | 10.6 | 159 | 0.001
Project #191 | 11.2 | 168 | 0.001
Project #192 | 13.1 | 196.5 | 0.001
Project #193 | 11.6 | 174 | 0.001
Project #194 | 12.4 | 186 | 0.001
Project #195 | 12.6 | 189 | 0.001
Project #196 | 7.5 | 112.5 | 0.001
Project #197 | 11.7 | 175.5 | 0.001
Project #198 | 12.2 | 183 | 0.001
Project #199 | 8.1 | 121.5 | 0.001
Project #200 | 16.1 | 241.5 | 0.001
Project #201 | 9.5 | 142.5 | 0.001
Project #202 | 13.3 | 199.5 | 0.001
Project #203 | 13 | 195 | 0.001
Project #204 | 8 | 120 | 0.001
Project #205 | 6.3 | 94.5 | 0.001
Project #206 | 10.4 | 156 | 0.001
Project #207 | 11.8 | 177 | 0.001
Project #208 | 9.4 | 141 | 0.001
Project #209 | 10.5 | 157.5 | 0.001
Project #210 | 8 | 120 | 0.001
Project #211 | 13.2 | 198 | 0.001
Project #212 | 7 | 105 | 0.001
Project #213 | 6.4 | 96 | 0.001
Project #214 | 13.1 | 196.5 | 0.001
Project #215 | 9.5 | 142.5 | 0.001
Project #216 | 14 | 210 | 0.001
Project #217 | 8.7 | 130.5 | 0.001
Project #218 | 10.9 | 163.5 | 0.001
Project #219 | 8.1 | 121.5 | 0.001
Project #220 | 15.1 | 226.5 | 0.001
Project #221 | 9.5 | 142.5 | 0.001
Project #222 | 11.9 | 178.5 | 0.001
Project #223 | 13 | 195 | 0.001
Project #224 | 9.6 | 144 | 0.001
Project #225 | 8.6 | 129 | 0.001
Project #226 | 13.8 | 207 | 0.001
Project #227 | 8.6 | 129 | 0.001
Project #228 | 11.1 | 166.5 | 0.001
Project #229 | 10.9 | 163.5 | 0.001
Project #230 | 10.4 | 156 | 0.001
Project #231 | 11.3 | 169.5 | 0.001
Project #232 | 8.1 | 121.5 | 0.001
Project #233 | 9.8 | 147 | 0.001
Project #234 | 10.2 | 153 | 0.001
Project #235 | 10.7 | 160.5 | 0.001
Project #236 | 11.4 | 171 | 0.001
Project #237 | 13.9 | 208.5 | 0.001
Project #238 | 9.1 | 136.5 | 0.001
Project #239 | 14.5 | 217.5 | 0.001
Project #240 | 7.1 | 106.5 | 0.001
Project #241 | 14.4 | 216 | 0.001
Project #242 | 12.7 | 190.5 | 0.001
Project #243 | 11.1 | 166.5 | 0.001
Project #244 | 6.1 | 91.5 | 0.001
Project #245 | 10.6 | 159 | 0.001
Project #246 | 12.5 | 187.5 | 0.001
Project #247 | 13.3 | 199.5 | 0.001
Project #248 | 15.8 | 237 | 0.001
Project #249 | 5.9 | 88.5 | 0.001
Project #250 | 10.8 | 162 | 0.001
Project #251 | 12.4 | 186 | 0.001
Project #252 | 7.6 | 114 | 0.001
Project #253 | 9.2 | 138 | 0.001
Project #254 | 10.4 | 156 | 0.001
Project #255 | 12.9 | 193.5 | 0.001
Project #256 | 10.4 | 156 | 0.001
Project #257 | 8.8 | 132 | 0.001
Project #258 | 11.9 | 178.5 | 0.001
Project #259 | 12 | 180 | 0.001
Project #260 | 13.3 | 199.5 | 0.001
Project #261 | 12.5 | 187.5 | 0.001
Project #262 | 9.4 | 141 | 0.001
Project #263 | 6.4 | 96 | 0.001
Project #264 | 7.8 | 117 | 0.001
Project #265 | 10.6 | 159 | 0.001
Project #266 | 11.2 | 168 | 0.001
Project #267 | 12.3 | 184.5 | 0.001
Project #268 | 12.1 | 181.5 | 0.001
Project #269 | 14.1 | 211.5 | 0.001
Project #270 | 11.4 | 171 | 0.001
Project #271 | 10.3 | 154.5 | 0.001
Project #272 | 11.5 | 172.5 | 0.001
Project #273 | 12.3 | 184.5 | 0.001
Project #274 | 11.5 | 172.5 | 0.001
Project #275 | 11.2 | 168 | 0.001
Project #276 | 10.6 | 159 | 0.001
Project #277 | 12.8 | 192 | 0.001
Project #278 | 17 | 255 | 0.001
Project #279 | 11.3 | 169.5 | 0.001
Project #280 | 11.4 | 171 | 0.001
Project #281 | 13.3 | 199.5 | 0.001
Project #282 | 8.6 | 129 | 0.001
Project #283 | 8.7 | 130.5 | 0.001
Project #284 | 12.8 | 192 | 0.001
Project #285 | 7.6 | 114 | 0.001
Project #286 | 9.8 | 147 | 0.001
Project #287 | 12.1 | 181.5 | 0.001
Project #288 | 7.4 | 111 | 0.001
Project #289 | 15.8 | 237 | 0.001
Project #290 | 14.9 | 223.5 | 0.001
Project #291 | 8.6 | 129 | 0.001
Project #292 | 14.4 | 216 | 0.001
Project #293 | 14.9 | 223.5 | 0.001
Project #294 | 8 | 120 | 0.001
Project #295 | 11.7 | 175.5 | 0.001
Project #296 | 9.8 | 147 | 0.001
Project #297 | 12.2 | 183 | 0.001
Project #298 | 9 | 135 | 0.001
Project #299 | 11.3 | 169.5 | 0.001
Project #300 | 11.4 | 171 | 0.001
Project #301 | 13.1 | 196.5 | 0.001
Project #302 | 9.5 | 142.5 | 0.001
Project #303 | 10.4 | 156 | 0.001
Project #304 | 11 | 165 | 0.001
Project #305 | 11.6 | 174 | 0.001
Project #306 | 11.8 | 177 | 0.001
Project #307 | 10.1 | 151.5 | 0.001
Project #308 | 9.9 | 148.5 | 0.001
Project #309 | 11 | 165 | 0.001
Project #310 | 16.4 | 246 | 0.001
Project #311 | 12.5 | 187.5 | 0.001
Project #312 | 12.8 | 192 | 0.001
Project #313 | 11.3 | 169.5 | 0.001
Project #314 | 6.2 | 93 | 0.001
Project #315 | 13 | 195 | 0.001
Project #316 | 15.1 | 226.5 | 0.001
Project #317 | 10.3 | 154.5 | 0.001
Project #318 | 9.9 | 148.5 | 0.001
Project #319 | 12.9 | 193.5 | 0.001
Project #320 | 11.1 | 166.5 | 0.001
Project #321 | 8.9 | 133.5 | 0.001
Project #322 | 7.5 | 112.5 | 0.001
Project #323 | 10.4 | 156 | 0.001
Project #324 | 12.1 | 181.5 | 0.001
Project #325 | 11.5 | 172.5 | 0.001
Project #326 | 10.6 | 159 | 0.001
Project #327 | 12.2 | 183 | 0.001
Project #328 | 8.8 | 132 | 0.001
Project #329 | 14 | 210 | 0.001
Project #330 | 10.8 | 162 | 0.001
Project #331 | 10.1 | 151.5 | 0.001
Project #332 | 10.8 | 162 | 0.001
Project #333 | 11 | 165 | 0.001
Project #334 | 15 | 225 | 0.001
Project #335 | 9.3 | 139.5 | 0.001
Project #336 | 8.3 | 124.5 | 0.001
Project #337 | 15.2 | 228 | 0.001
Project #338 | 11 | 165 | 0.001
Project #339 | 13.1 | 196.5 | 0.001
Project #340 | 9.4 | 141 | 0.001
Project #341 | 7.9 | 118.5 | 0.001
Project #342 | 9.2 | 138 | 0.001
Project #343 | 8.9 | 133.5 | 0.001
Project #344 | 12.7 | 190.5 | 0.001
Project #345 | 12.2 | 183 | 0.001
Project #346 | 11.4 | 171 | 0.001
Project #347 | 11.9 | 178.5 | 0.001
Project #348 | 13.1 | 196.5 | 0.001
Project #349 | 8.8 | 132 | 0.001
Project #350 | 14.6 | 219 | 0.001
Project #351 | 9.9 | 148.5 | 0.001
Project #352 | 9.3 | 139.5 | 0.001
Project #353 | 15.4 | 231 | 0.001
Project #354 | 9.5 | 142.5 | 0.001
Project #355 | 11.1 | 166.5 | 0.001
Project #356 | 11.3 | 169.5 | 0.001
Project #357 | 10.5 | 157.5 | 0.001
Project #358 | 11 | 165 | 0.001
Project #359 | 9.9 | 148.5 | 0.001
Project #360 | 12.9 | 193.5 | 0.001
Project #361 | 11 | 165 | 0.001
Project #362 | 9.8 | 147 | 0.001
Project #363 | 9.8 | 147 | 0.001
Project #364 | 11.6 | 174 | 0.001
Project #365 | 14.9 | 223.5 | 0.001
Project #366 | 11.9 | 178.5 | 0.001
Project #367 | 10.8 | 162 | 0.001
Project #368 | 7 | 105 | 0.001
Project #369 | 10.7 | 160.5 | 0.001
Project #370 | 11.7 | 175.5 | 0.001
Project #371 | 13.3 | 199.5 | 0.001
Project #372 | 8.2 | 123 | 0.001
Project #373 | 9.4 | 141 | 0.001
Project #374 | 6.3 | 94.5 | 0.001
Project #375 | 11.8 | 177 | 0.001
Project #376 | 9.7 | 145.5 | 0.001
Project #377 | 11 | 165 | 0.001
Project #378 | 14.1 | 211.5 | 0.001
Project #379 | 10.6 | 159 | 0.001
Project #380 | 12.9 | 193.5 | 0.001
Project #381 | 11.3 | 169.5 | 0.001
Project #382 | 10 | 150 | 0.001
Project #383 | 17 | 255 | 0.001
Project #384 | 9.8 | 147 | 0.001
Project #385 | 9.3 | 139.5 | 0.001
Project #386 | 9.7 | 145.5 | 0.001
Project #387 | 13.1 | 196.5 | 0.001
Project #388 | 9.7 | 145.5 | 0.001
Project #389 | 6.4 | 96 | 0.001
Project #390 | 8.8 | 132 | 0.001
Project #391 | 8 | 120 | 0.001
Project #392 | 11 | 165 | 0.001
Project #393 | 11.7 | 175.5 | 0.001
Project #394 | 10.8 | 162 | 0.001
Project #395 | 11.7 | 175.5 | 0.001
Project #396 | 8.5 | 127.5 | 0.001
Project #397 | 9.9 | 148.5 | 0.001
Project #398 | 6.7 | 100.5 | 0.001
Project #399 | 9.3 | 139.5 | 0.001
Project #400 | 9.6 | 144 | 0.001
Project #401 | 9.4 | 141 | 0.001
Project #402 | 12.6 | 189 | 0.001
Project #403 | 10.7 | 160.5 | 0.001
Project #404 | 15 | 225 | 0.001
Project #405 | 10 | 150 | 0.001
Project #406 | 12.5 | 187.5 | 0.001
Project #407 | 13.1 | 196.5 | 0.001
Project #408 | 10.3 | 154.5 | 0.001
Project #409 | 8.8 | 132 | 0.001
Project #410 | 8.4 | 126 | 0.001
Project #411 | 11.8 | 177 | 0.001
Project #412 | 15.7 | 235.5 | 0.001
Project #413 | 6.9 | 103.5 | 0.001
Project #414 | 7.4 | 111 | 0.001
Project #415 | 9.5 | 142.5 | 0.001
Project #416 | 9.3 | 139.5 | 0.001
Project #417 | 7.8 | 117 | 0.001
Project #418 | 10.4 | 156 | 0.001
Project #419 | 14.8 | 222 | 0.001
Project #420 | 10.2 | 153 | 0.001
Project #421 | 11.6 | 174 | 0.001
Project #422 | 8.9 | 133.5 | 0.001
Project #423 | 15.9 | 238.5 | 0.001
Project #424 | 11.3 | 169.5 | 0.001
Project #425 | 12 | 180 | 0.001
Project #426 | 13.2 | 198 | 0.001
Project #427 | 12.7 | 190.5 | 0.001
Project #428 | 12.5 | 187.5 | 0.001
Project #429 | 13.3 | 199.5 | 0.001
Project #430 | 16.4 | 246 | 0.001
Project #431 | 12.5 | 187.5 | 0.001
Project #432 | 14.5 | 217.5 | 0.001
Project #433 | 11.3 | 169.5 | 0.001
Project #434 | 8.8 | 132 | 0.001
Project #435 | 8.7 | 130.5 | 0.001
Project #436 | 12.2 | 183 | 0.001
Project #437 | 6.9 | 103.5 | 0.001
Project #438 | 14.2 | 213 | 0.001
Project #439 | 12.6 | 189 | 0.001
Project #440 | 10.1 | 151.5 | 0.001
Project #441 | 10.8 | 162 | 0.001
Project #442 | 13.2 | 198 | 0.001
Project #443 | 9.6 | 144 | 0.001
Project #444 | 9 | 135 | 0.001
Project #445 | 12 | 180 | 0.001
Project #446 | 8.7 | 130.5 | 0.001
Project #447 | 14.2 | 213 | 0.001
Project #448 | 9.6 | 144 | 0.001
Project #449 | 11.7 | 175.5 | 0.001
Project #450 | 14.7 | 220.5 | 0.001
Project #451 | 9.3 | 139.5 | 0.001
Project #452 | 8.9 | 133.5 | 0.001
Project #453 | 9.5 | 142.5 | 0.001
Project #454 | 9.7 | 145.5 | 0.001
Project #455 | 9.7 | 145.5 | 0.001
Project #456 | 10.7 | 160.5 | 0.001
Project #457 | 14.1 | 211.5 | 0.001
Project #458 | 12.2 | 183 | 0.001
Project #459 | 11.3 | 169.5 | 0.001
Project #460 | 9.8 | 147 | 0.001
Project #461 | 7.5 | 112.5 | 0.001
Project #462 | 15.3 | 229.5 | 0.001
Project #463 | 12.5 | 187.5 | 0.001
Project #464 | 15.1 | 226.5 | 0.001
Project #465 | 10.6 | 159 | 0.001
Project #466 | 9 | 135 | 0.001
Project #467 | 12.2 | 183 | 0.001
Project #468 | 10.7 | 160.5 | 0.001
Project #469 | 5.2 | 78 | 0.001
Project #470 | 15.5 | 232.5 | 0.001
Project #471 | 8.6 | 129 | 0.001
Project #472 | 8.7 | 130.5 | 0.001
Project #473 | 8.4 | 126 | 0.001
Project #474 | 6.8 | 102 | 0.001
Project #475 | 6.1 | 91.5 | 0.001
Project #476 | 11.3 | 169.5 | 0.001
Project #477 | 11.8 | 177 | 0.001
Project #478 | 10 | 150 | 0.001
Project #479 | 7.1 | 106.5 | 0.001
Project #480 | 9.5 | 142.5 | 0.001
Project #481 | 8.4 | 126 | 0.001
Project #482 | 10.2 | 153 | 0.001
Project #483 | 14.2 | 213 | 0.001
Project #484 | 13.9 | 208.5 | 0.001
Project #485 | 13.2 | 198 | 0.001
Project #486 | 13.4 | 201 | 0.001
Project #487 | 12.1 | 181.5 | 0.001
Project #488 | 9.4 | 141 | 0.001
Project #489 | 10.4 | 156 | 0.001
Project #490 | 16.2 | 243 | 0.001
Project #491 | 8.7 | 130.5 | 0.001
Project #492 | 10.9 | 163.5 | 0.001
Project #493 | 11.4 | 171 | 0.001
Project #494 | 15 | 225 | 0.001
Project #495 | 11.9 | 178.5 | 0.001
Project #496 | 7.4 | 111 | 0.001
Project #497 | 12.1 | 181.5 | 0.001
Project #498 | 12.4 | 186 | 0.001
Project #499 | 9.9 | 148.5 | 0.001
Project #500 | 12 | 180 | 0.001
Project #501 | 10.1 | 151.5 | 0.001
Project #502 | 11 | 165 | 0.001
Project #503 | 8.5 | 127.5 | 0.001
Project #504 | 10.2 | 153 | 0.001
Project #505 | 11.4 | 171 | 0.001
Project #506 | 9.6 | 144 | 0.001
Project #507 | 10.4 | 156 | 0.001
Project #508 | 9.6 | 144 | 0.001
Project #509 | 14.2 | 213 | 0.001
Project #510 | 9.6 | 144 | 0.001
Project #511 | 6.8 | 102 | 0.001
Project #512 | 13.8 | 207 | 0.001
Project #513 | 11.3 | 169.5 | 0.001
Project #514 | 13.2 | 198 | 0.001
Project #515 | 10.4 | 156 | 0.001
Project #516 | 12.2 | 183 | 0.001
Project #517 | 11.9 | 178.5 | 0.001
Project #518 | 11.4 | 171 | 0.001
Project #519 | 11.8 | 177 | 0.001
Project #520 | 9.4 | 141 | 0.001
Project #521 | 10 | 150 | 0.001
Project #522 | 7.9 | 118.5 | 0.001
Project #523 | 8.7 | 130.5 | 0.001
Project #524 | 12.9 | 193.5 | 0.001
Project #525 | 10.4 | 156 | 0.001
Project #526 | 12.7 | 190.5 | 0.001
Project #527 | 7.4 | 111 | 0.001
Project #528 | 9.8 | 147 | 0.001
Project #529 | 14.3 | 214.5 | 0.001
Project #530 | 15.6 | 234 | 0.001
Project #531 | 9.4 | 141 | 0.001
Project #532 | 8.6 | 129 | 0.001
Project #533 | 10.6 | 159 | 0.001
Project #534 | 9.7 | 145.5 | 0.001
Project #535 | 14 | 210 | 0.001
Project #536 | 14.8 | 222 | 0.001
Project #537 | 11.6 | 174 | 0.001
Project #538 | 10.7 | 160.5 | 0.001
Project #539 | 10.2 | 153 | 0.001
Project #540 | 11.6 | 174 | 0.001
Project #541 | 9.9 | 148.5 | 0.001
Project #542 | 8.9 | 133.5 | 0.001
Project #543 | 11.5 | 172.5 | 0.001
Project #544 | 9 | 135 | 0.001
Project #545 | 10.5 | 157.5 | 0.001
Project #546 | 11.8 | 177 | 0.001
Project #547 | 11.5 | 172.5 | 0.001
Project #548 | 10.9 | 163.5 | 0.001
Project #549 | 11.8 | 177 | 0.001
Project #550 | 11.4 | 171 | 0.001
Project #551 | 7.4 | 111 | 0.001
Project #552 | 10.3 | 154.5 | 0.001
Project #553 | 8.6 | 129 | 0.001
Project #554 | 12.8 | 192 | 0.001
Project #555 | 9.4 | 141 | 0.001
Project #556 | 10.7 | 160.5 | 0.001
Project #557 | 10.2 | 153 | 0.001
Project #558 | 12.3 | 184.5 | 0.001
Project #559 | 13.2 | 198 | 0.001
Project #560 | 12.3 | 184.5 | 0.001
Project #561 | 9.9 | 148.5 | 0.001
Project #562 | 11.7 | 175.5 | 0.001
Project #563 | 9.9 | 148.5 | 0.001
Project #564 | 12.8 | 192 | 0.001
Project #565 | 11.1 | 166.5 | 0.001
Project #566 | 8.4 | 126 | 0.001
Project #567 | 9.7 | 145.5 | 0.001
Project #568 | 10.4 | 156 | 0.001
Project #569 | 11.9 | 178.5 | 0.001
Project #570 | 12.2 | 183 | 0.001
Project #571 | 8.7 | 130.5 | 0.001
Project #572 | 9.8 | 147 | 0.001
Project #573 | 13.6 | 204 | 0.001
Project #574 | 7.1 | 106.5 | 0.001
Project #575 | 9.1 | 136.5 | 0.001
Project #576 | 11.1 | 166.5 | 0.001
Project #577 | 14 | 210 | 0.001
Project #578 | 10.3 | 154.5 | 0.001
Project #579 | 12 | 180 | 0.001
Project #580 | 8.6 | 129 | 0.001
Project #581 | 10.9 | 163.5 | 0.001
Project #582 | 10.6 | 159 | 0.001
Project #583 | 8.7 | 130.5 | 0.001
Project #584 | 8.2 | 123 | 0.001
Project #585 | 9.8 | 147 | 0.001
Project #586 | 14 | 210 | 0.001
Project #587 | 13.2 | 198 | 0.001
Project #588 | 8.9 | 133.5 | 0.001
Project #589 | 10.6 | 159 | 0.001
Project #590 | 10.1 | 151.5 | 0.001
Project #591 | 9.7 | 145.5 | 0.001
Project #592 | 12.1 | 181.5 | 0.001
Project #593 | 11.4 | 171 | 0.001
Project #594 | 9 | 135 | 0.001
Project #595 | 9.7 | 145.5 | 0.001
Project #596 | 10.2 | 153 | 0.001
Project #597 | 13.4 | 201 | 0.001
Project #598 | 13.4 | 201 | 0.001
Project #599 | 8.8 | 132 | 0.001
Project #600 | 11.8 | 177 | 0.001
Project #601 | 10.4 | 156 | 0.001
Project #602 | 11.5 | 172.5 | 0.001
Project #603 | 11.8 | 177 | 0.001
Project #604 | 9.8 | 147 | 0.001
Project #605 | 11.3 | 169.5 | 0.001
Project #606 | 11.7 | 175.5 | 0.001
Project #607 | 10.5 | 157.5 | 0.001
Project #608 | 14.1 | 211.5 | 0.001
Project #609 | 15.3 | 229.5 | 0.001
Project #610 | 10.9 | 163.5 | 0.001
Project #611 | 5.9 | 88.5 | 0.001
Project #612 | 9.4 | 141 | 0.001
Project #613 | 11 | 165 | 0.001
Project #614 | 8.6 | 129 | 0.001
Project #615 | 11.1 | 166.5 | 0.001
Project #616 | 11.6 | 174 | 0.001
Project #617 | 15.3 | 229.5 | 0.001
Project #618 | 13.5 | 202.5 | 0.001
Project #619 | 14 | 210 | 0.001
Project #620 | 8.8 | 132 | 0.001
Project #621 | 7.1 | 106.5 | 0.001
Project #622 | 14.8 | 222 | 0.001
Project #623 | 10.6 | 159 | 0.001
Project #624 | 10.1 | 151.5 | 0.001
Project #625 | 11.4 | 171 | 0.001
Project #626 | 14.7 | 220.5 | 0.001
Project #627 | 11.3 | 169.5 | 0.001
Project #628 | 12 | 180 | 0.001
Project #629 | 13.4 | 201 | 0.001
Project #630 | 10.7 | 160.5 | 0.001
Project #631 | 11.3 | 169.5 | 0.001
Project #632 | 10.3 | 154.5 | 0.001
Project #633 | 8.3 | 124.5 | 0.001
Project #634 | 9.4 | 141 | 0.001
Project #635 | 9.1 | 136.5 | 0.001
Project #636 | 11.5 | 172.5 | 0.001
Project #637 | 9 | 135 | 0.001
Project #638 | 7.1 | 106.5 | 0.001
Project #639 | 10 | 150 | 0.001
Project #640 | 13.3 | 199.5 | 0.001
Project #641 | 11.4 | 171 | 0.001
Project #642 | 12.2 | 183 | 0.001
Project #643 | 11.5 | 172.5 | 0.001
Project #644 | 10.9 | 163.5 | 0.001
Project #645 | 11.2 | 168 | 0.001
Project #646 | 10.5 | 157.5 | 0.001
Project #647 | 9.7 | 145.5 | 0.001
Project #648 | 9.9 | 148.5 | 0.001
Project #649 | 14.2 | 213 | 0.001
Project #650 | 13.6 | 204 | 0.001
Project #651 | 17.2 | 258 | 0.001
Project #652 | 9.6 | 144 | 0.001
Project #653 | 10.1 | 151.5 | 0.001
Project #654 | 10.7 | 160.5 | 0.001
Project #655 | 10.5 | 157.5 | 0.001
Project #656 | 13.4 | 201 | 0.001
Project #657 | 10 | 150 | 0.001
Project #658 | 7.3 | 109.5 | 0.001
Project #659 | 11.9 | 178.5 | 0.001
Project #660 | 8.8 | 132 | 0.001
Project #661 | 13.2 | 198 | 0.001
Project #662 | 6.7 | 100.5 | 0.001
Project #663 | 12.4 | 186 | 0.001
Project #664 | 9.3 | 139.5 | 0.001
Project #665 | 11.3 | 169.5 | 0.001
Project #666 | 9.3 | 139.5 | 0.001
Project #667 | 7.2 | 108 | 0.001
Project #668 | 11 | 165 | 0.001
Project #669 | 13.7 | 205.5 | 0.001
Project #670 | 9 | 135 | 0.001
Project #671 | 11.5 | 172.5 | 0.001
Project #672 | 10.8 | 162 | 0.001
Project #673 | 8.6 | 129 | 0.001
Project #674 | 10.2 | 153 | 0.001
Project #675 | 13.8 | 207 | 0.001
Project #676 | 10.2 | 153 | 0.001
Project #677 | 6.7 | 100.5 | 0.001
Project #678 | 11.2 | 168 | 0.001
Project #679 | 13 | 195 | 0.001
Project #680 | 11.4 | 171 | 0.001
Project #681 | 13 | 195 | 0.001
Project #682 | 10.1 | 151.5 | 0.001
Project #683 | 10 | 150 | 0.001
Project #684 | 11.9 | 178.5 | 0.001
Project #685 | 9.4 | 141 | 0.001
Project #686 | 10.1 | 151.5 | 0.001
Project #687 | 12.8 | 192 | 0.001
Project #688 | 11.2 | 168 | 0.001
Project #689 | 9.7 | 145.5 | 0.001
Project #690 | 8.7 | 130.5 | 0.001
Project #691 | 7.5 | 112.5 | 0.001
Project #692 | 12.4 | 186 | 0.001
Project #693 | 10.1 | 151.5 | 0.001
Project #694 | 9 | 135 | 0.001
Project #695 | 10.1 | 151.5 | 0.001
Project #696 | 13.4 | 201 | 0.001
Project #697 | 11.9 | 178.5 | 0.001
Project #698 | 10.7 | 160.5 | 0.001
Project #699 | 8 | 120 | 0.001
Project #700 | 10.7 | 160.5 | 0.001
Project #701 | 10 | 150 | 0.001
Project #702 | 11.6 | 174 | 0.001
Project #703 | 12.9 | 193.5 | 0.001
Project #704 | 11.5 | 172.5 | 0.001
Project #705 | 10.3 | 154.5 | 0.001
Project #706 | 14.6 | 219 | 0.001
Project #707 | 13.1 | 196.5 | 0.001
Project #708 | 13.7 | 205.5 | 0.001
Project #709 | 9.7 | 145.5 | 0.001
Project #710 | 12.9 | 193.5 | 0.001
Project #711 | 17.3 | 259.5 | 0.001
Project #712 | 10.7 | 160.5 | 0.001
Project #713 | 13.3 | 199.5 | 0.001
Project #714 | 10 | 150 | 0.001
Project #715 | 12.2 | 183 | 0.001
Project #716 | 9.8 | 147 | 0.001
Project #717 | 11.8 | 177 | 0.001
Project #718 | 12.4 | 186 | 0.001
Project #719 | 12 | 180 | 0.001
Project #720 | 12.2 | 183 | 0.001
Project #721 | 12.9 | 193.5 | 0.001
Project #722 | 9.8 | 147 | 0.001
Project #723 | 12.4 | 186 | 0.001
Project #724 | 12.3 | 184.5 | 0.001
Project #725 | 7.3 | 109.5 | 0.001
Project #726 | 13 | 195 | 0.001
Project #727 | 7.9 | 118.5 | 0.001
Project #728 | 9.7 | 145.5 | 0.001
Project #729 | 14.9 | 223.5 | 0.001
Project #730 | 9.7 | 145.5 | 0.001
Project #731 | 9.2 | 138 | 0.001
Project #732 | 11.2 | 168 | 0.001
Project #733 | 10.8 | 162 | 0.001
Project #734 | 8.3 | 124.5 | 0.001
Project #735 | 12 | 180 | 0.001
Project #736 | 7.7 | 115.5 | 0.001
Project #737 | 11 | 165 | 0.001
Project #738 | 8.6 | 129 | 0.001
Project #739 | 10 | 150 | 0.001
Project #740 | 9.9 | 148.5 | 0.001
Project #741 | 13.7 | 205.5 | 0.001
Project #742 | 12.4 | 186 | 0.001
Project #743 | 9.1 | 136.5 | 0.001
Project #744 | 8.6 | 129 | 0.001
Project #745 | 9.6 | 144 | 0.001
Project #746 | 9.3 | 139.5 | 0.001
Project #747 | 14.5 | 217.5 | 0.001
Project #748 | 7.8 | 117 | 0.001
Project #749 | 8.6 | 129 | 0.001
Project #750 | 12.1 | 181.5 | 0.001
Project #751 | 10.1 | 151.5 | 0.001
Project #752 | 8.5 | 127.5 | 0.001
Project #753 | 13.1 | 196.5 | 0.001
Project #754 | 9 | 135 | 0.001
Project #755 | 11.2 | 168 | 0.001
Project #756 | 8.3 | 124.5 | 0.001
Project #757 | 11.6 | 174 | 0.001
Project #758 | 12.7 | 190.5 | 0.001
Project #759 | 11.8 | 177 | 0.001
Project #760 | 8.3 | 124.5 | 0.001
Project #761 | 9.3 | 139.5 | 0.001
Project #762 | 7.4 | 111 | 0.001
Project #763 | 8.8 | 132 | 0.001
Project #764 | 12.1 | 181.5 | 0.001
Project #765 | 6.8 | 102 | 0.001
Project #766 | 11.3 | 169.5 | 0.001
Project #767 | 12.4 | 186 | 0.001
Project #768 | 8.4 | 126 | 0.001
Project #769 | 9.6 | 144 | 0.001
Project #770 | 15 | 225 | 0.001
Project #771 | 11.3 | 169.5 | 0.001
Project #772 | 12.7 | 190.5 | 0.001
Project #773 | 10.5 | 157.5 | 0.001
Project #774 | 13.4 | 201 | 0.001
Project #775 | 8.5 | 127.5 | 0.001
Project #776 | 12.5 | 187.5 | 0.001
Project #777 | 12.7 | 190.5 | 0.001
Project #778 | 14.6 | 219 | 0.001
Project #779 | 9.9 | 148.5 | 0.001
Project #780 | 11.7 | 175.5 | 0.001
Project #781 | 9.8 | 147 | 0.001
Project #782 | 9.8 | 147 | 0.001
Project #783 | 10.1 | 151.5 | 0.001
Project #784 | 12.4 | 186 | 0.001
Project #785 | 8.1 | 121.5 | 0.001
Project #786 | 8.6 | 129 | 0.001
Project #787 | 13.5 | 202.5 | 0.001
Project #788 | 9.9 | 148.5 | 0.001
Project #789 | 12.2 | 183 | 0.001
Project #790 | 10.5 | 157.5 | 0.001
Project #791 | 11.3 | 169.5 | 0.001
Project #792 | 14.7 | 220.5 | 0.001
Project #793 | 13.3 | 199.5 | 0.001
Project #794 | 10.3 | 154.5 | 0.001
Project #795 | 5.9 | 88.5 | 0.001
Project #796 | 12.6 | 189 | 0.001
Project #797 | 9.9 | 148.5 | 0.001
Project #798 | 9.6 | 144 | 0.001
Project #799 | 8.7 | 130.5 | 0.001
Project #800 | 7 | 105 | 0.001
Project #801 | 11.2 | 168 | 0.001
Project #802 | 7.8 | 117 | 0.001
Project #803 | 13.6 | 204 | 0.001
Project #804 | 13.4 | 201 | 0.001
Project #805 | 13 | 195 | 0.001
Project #806 | 10.3 | 154.5 | 0.001
Project #807 | 10.2 | 153 | 0.001
Project #808 | 14.6 | 219 | 0.001
Project #809 | 9.8 | 147 | 0.001
Project #810 | 14.9 | 223.5 | 0.001
Project #811 | 12.2 | 183 | 0.001
Project #812 | 8.5 | 127.5 | 0.001
Project #813 | 7.6 | 114 | 0.001
Project #814 | 8.2 | 123 | 0.001
Project #815 | 8.9 | 133.5 | 0.001
Project #816 | 8.6 | 129 | 0.001
Project #817 | 7.1 | 106.5 | 0.001
Project #818 | 11.8 | 177 | 0.001
Project #819 | 9.3 | 139.5 | 0.001
Project #820 | 10.3 | 154.5 | 0.001
Project #821 | 8.7 | 130.5 | 0.001
Project #822 | 8.7 | 130.5 | 0.001
Project #823 | 11.2 | 168 | 0.001
Project #824 | 11.7 | 175.5 | 0.001
Project #825 | 9.3 | 139.5 | 0.001
Project #826 | 13.3 | 199.5 | 0.001
Project #827 | 12.1 | 181.5 | 0.001
Project #828 | 11.1 | 166.5 | 0.001
Project #829 | 9.9 | 148.5 | 0.001
Project #830 | 8.3 | 124.5 | 0.001
Project #831 | 13.5 | 202.5 | 0.001
Project #832 | 11.2 | 168 | 0.001
Project #833 | 13.7 | 205.5 | 0.001
Project #834 | 8.7 | 130.5 | 0.001
Project #835 | 15 | 225 | 0.001
Project #836 | 11 | 165 | 0.001
Project #837 | 9.7 | 145.5 | 0.001
Project #838 | 12 | 180 | 0.001
Project #839 | 12.7 | 190.5 | 0.001
Project #840 | 11.3 | 169.5 | 0.001
Project #841 | 16.8 | 252 | 0.001
Project #842 | 7.6 | 114 | 0.001
Project #843 | 11.1 | 166.5 | 0.001
Project #844 | 9.4 | 141 | 0.001
Project #845 | 11.1 | 166.5 | 0.001
Project #846 | 11.2 | 168 | 0.001
Project #847 | 12.9 | 193.5 | 0.001
Project #848 | 11.6 | 174 | 0.001
Project #849 | 13.5 | 202.5 | 0.001
Project #850 | 9.9 | 148.5 | 0.001
Project #851 | 14.4 | 216 | 0.001
Project #852 | 13 | 195 | 0.001
Project #853 | 12.3 | 184.5 | 0.001
Project #854 | 12.6 | 189 | 0.001
Project #855 | 9.8 | 147 | 0.001
Project #856 | 8.9 | 133.5 | 0.001
Project #857 | 13.7 | 205.5 | 0.001
Project #858 | 13.7 | 205.5 | 0.001
Project #859 | 6.5 | 97.5 | 0.001
Project #860 | 12.7 | 190.5 | 0.001
Project #861 | 11.6 | 174 | 0.001
Project #862 | 10.4 | 156 | 0.001
Project #863 | 13.7 | 205.5 | 0.001
Project #864 | 10.7 | 160.5 | 0.001
Project #865 | 12.2 | 183 | 0.001
Project #866 | 10.7 | 160.5 | 0.001
Project #867 | 7.4 | 111 | 0.001
Project #868 | 10.8 | 162 | 0.001
Project #869 | 10.2 | 153 | 0.001
Project #870 | 15.6 | 234 | 0.001
Project #871 | 14.2 | 213 | 0.001
Project #872 | 8.7 | 130.5 | 0.001
Project #873 | 13.2 | 198 | 0.001
Project #874 | 11.4 | 171 | 0.001
Project #875 | 10.5 | 157.5 | 0.001
Project #876 | 8.3 | 124.5 | 0.001
Project #877 | 10.9 | 163.5 | 0.001
Project #878 | 8.7 | 130.5 | 0.001
Project #879 | 9.2 | 138 | 0.001
Project #880 | 14.3 | 214.5 | 0.001
Project #881 | 7.5 | 112.5 | 0.001
Project #882 | 13.4 | 201 | 0.001
Project #883 | 9.7 | 145.5 | 0.001
Project #884 | 5.2 | 78 | 0.001
Project #885 | 12.2 | 183 | 0.001
Project #886 | 6.8 | 102 | 0.001
Project #887 | 11.2 | 168 | 0.001
Project #888 | 12.2 | 183 | 0.001
Project #889 | 11.9 | 178.5 | 0.001
Project #890 | 10.9 | 163.5 | 0.001
Project #891 | 10 | 150 | 0.001
Project #892 | 12.1 | 181.5 | 0.001
Project #893 | 7.8 | 117 | 0.001
Project #894 | 6.3 | 94.5 | 0.001
Project #895 | 7.5 | 112.5 | 0.001
Project #896 | 10.8 | 162 | 0.001
Project #897 | 7.1 | 106.5 | 0.001
Project #898 | 9.4 | 141 | 0.001
Project #899 | 12 | 180 | 0.001
Project #900 | 11.2 | 168 | 0.001
Project #901 | 11 | 165 | 0.001
Project #902 | 9 | 135 | 0.001
Project #903 | 9.4 | 141 | 0.001
Project #904 | 10.9 | 163.5 | 0.001
Project #905 | 11.9 | 178.5 | 0.001
Project #906 | 14.5 | 217.5 | 0.001
Project #907 | 13.6 | 204 | 0.001
Project #908 | 11 | 165 | 0.001
Project #909 | 10.4 | 156 | 0.001
Project #910 | 13.5 | 202.5 | 0.001
Project #911 | 10.9 | 163.5 | 0.001
Project #912 | 14.5 | 217.5 | 0.001
Project #913 | 13.1 | 196.5 | 0.001
Project #914 | 12.3 | 184.5 | 0.001
Project #915 | 15 | 225 | 0.001
Project #916 | 14 | 210 | 0.001
Project #917 | 9.9 | 148.5 | 0.001
Project #918 | 12.9 | 193.5 | 0.001
Project #919 | 10.4 | 156 | 0.001
Project #920 | 13.2 | 198 | 0.001
Project #921 | 16 | 240 | 0.001
Project #922 | 13.2 | 198 | 0.001
Project #923 | 11.3 | 169.5 | 0.001
Project #924 | 8.4 | 126 | 0.001
Project #925 | 14.2 | 213 | 0.001
Project #926 | 12.5 | 187.5 | 0.001
Project #927 | 13.9 | 208.5 | 0.001
Project #928 | 11.6 | 174 | 0.001
Project #929 | 9.6 | 144 | 0.001
Project #930 | 8.2 | 123 | 0.001
Project #931 | 11.3 | 169.5 | 0.001
Project #932 | 9.4 | 141 | 0.001
Project #933 | 9.1 | 136.5 | 0.001
Project #934 | 12.7 | 190.5 | 0.001
Project #935 | 13.2 | 198 | 0.001
Project #936 | 13.1 | 196.5 | 0.001
Project #937 | 10.6 | 159 | 0.001
Project #938 | 13.2 | 198 | 0.001
Project #939 | 13.8 | 207 | 0.001
Project #940 | 12.8 | 192 | 0.001
Project #941 | 11.3 | 169.5 | 0.001
Project #942 | 12 | 180 | 0.001
Project #943 | 11.8 | 177 | 0.001
Project #944 | 10.6 | 159 | 0.001
Project #945 | 10 | 150 | 0.001
Project #946 | 7.3 | 109.5 | 0.001
Project #947 | 12.3 | 184.5 | 0.001
Project #948 | 10.2 | 153 | 0.001
Project #949 | 14.2 | 213 | 0.001
Project #950 | 13.8 | 207 | 0.001
Project #951 | 13.9 | 208.5 | 0.001
Project #952 | 10.8 | 162 | 0.001
Project #953 | 11.4 | 171 | 0.001
Project #954 | 11 | 165 | 0.001
Project #955 | 13.4 | 201 | 0.001
Project #956 | 10.8 | 162 | 0.001
Project #957 | 14.2 | 213 | 0.001
Project #958 | 10.4 | 156 | 0.001
Project #959 | 9.6 | 144 | 0.001
Project #960 | 8 | 120 | 0.001
Project #961 | 11.1 | 166.5 | 0.001
Project #962 | 13 | 195 | 0.001
Project #963 | 14.9 | 223.5 | 0.001
Project #964 | 8.6 | 129 | 0.001
Project #965 | 15.1 | 226.5 | 0.001
Project #966 | 10.5 | 157.5 | 0.001
Project #967 | 10.8 | 162 | 0.001
Project #968 | 8.7 | 130.5 | 0.001
Project #969 | 8.5 | 127.5 | 0.001
Project #970 | 10.9 | 163.5 | 0.001
Project #971 | 17.3 | 259.5 | 0.001
Project #972 | 12.4 | 186 | 0.001
Project #973 | 6.5 | 97.5 | 0.001
Project #974 | 11.7 | 175.5 | 0.001
Project #975 | 11.2 | 168 | 0.001
Project #976 | 9.1 | 136.5 | 0.001
Project #977 | 8.9 | 133.5 | 0.001
Project #978 | 15.1 | 226.5 | 0.001
Project #979 | 11.9 | 178.5 | 0.001
Project #980 | 10.6 | 159 | 0.001
Project #981 | 10.2 | 153 | 0.001
Project #982 | 10.2 | 153 | 0.001
Project #983 | 12.6 | 189 | 0.001
Project #984 | 9.2 | 138 | 0.001
Project #985 | 12.4 | 186 | 0.001
Project #986 | 10.3 | 154.5 | 0.001
Project #987 | 12 | 180 | 0.001
Project #988 | 9.3 | 139.5 | 0.001
Project #989 | 10.9 | 163.5 | 0.001
Project #990 | 14.1 | 211.5 | 0.001
Project #991 | 14.2 | 213 | 0.001
Project #992 | 9.8 | 147 | 0.001
Project #993 | 10.2 | 153 | 0.001
Project #994 | 13.3 | 199.5 | 0.001
Project #995 | 11.5 | 172.5 | 0.001
Project #996 | 6.7 | 100.5 | 0.001
Project #997 | 11.3 | 169.5 | 0.001
Project #998 | 12.3 | 184.5 | 0.001
Project #999 | 14.6 | 219 | 0.001
Project #1000 | 7.9 | 118.5 | 0.001

## 4. Aggregate
Confidence Intervals | Project Length
50% | 165
75% | 187.5
85% | 201
95% | 222
Row Labels | Time to Complete | Cumulative Probaility
Project #429 | 76.5 | 0.1%
Project #633 | 78 | 0.2%
Project #52 | 78 | 0.3%
Project #706 | 79.5 | 0.4%
Project #623 | 82.5 | 0.5%
Project #241 | 84 | 0.6%
Project #136 | 85.5 | 0.7%
Project #592 | 85.5 | 0.8%
Project #432 | 88.5 | 0.9%
Project #7 | 90 | 1%
Project #639 | 90 | 1.1%
Project #152 | 91.5 | 1.2%
Project #155 | 91.5 | 1.3%
Project #164 | 91.5 | 1.4%
Project #588 | 91.5 | 1.5%
Project #469 | 91.5 | 1.6%
Project #68 | 93 | 1.7%
Project #596 | 97.5 | 1.8%
Project #203 | 99 | 1.9%
Project #259 | 99 | 2%
Project #707 | 99 | 2.1%
Project #970 | 99 | 2.2%
Project #13 | 100.5 | 2.3%
Project #426 | 100.5 | 2.4%
Project #660 | 100.5 | 2.5%
Project #505 | 100.5 | 2.6%
Project #931 | 100.5 | 2.7%
Project #574 | 102 | 2.8%
Project #686 | 102 | 2.9%
Project #728 | 105 | 3%
Project #178 | 106.5 | 3.1%
Project #296 | 106.5 | 3.2%
Project #582 | 106.5 | 3.3%
Project #814 | 106.5 | 3.4%
Project #940 | 106.5 | 3.5%
Project #16 | 108 | 3.6%
Project #687 | 108 | 3.7%
Project #649 | 108 | 3.8%
Project #5 | 109.5 | 3.9%
Project #570 | 109.5 | 4%
Project #536 | 109.5 | 4.1%
Project #39 | 111 | 4.2%
Project #558 | 111 | 4.3%
Project #433 | 111 | 4.4%
Project #492 | 111 | 4.5%
Project #664 | 111 | 4.6%
Project #456 | 111 | 4.7%
Project #810 | 111 | 4.8%
Project #864 | 111 | 4.9%
Project #872 | 111 | 5%
Project #271 | 112.5 | 5.1%
Project #281 | 112.5 | 5.2%
Project #292 | 112.5 | 5.3%
Project #848 | 112.5 | 5.4%
Project #770 | 112.5 | 5.5%
Project #842 | 112.5 | 5.6%
Project #141 | 114 | 5.7%
Project #356 | 114 | 5.8%
Project #353 | 114 | 5.9%
Project #332 | 114 | 6%
Project #675 | 114 | 6.1%
Project #510 | 114 | 6.2%
Project #442 | 114 | 6.3%
Project #673 | 114 | 6.4%
Project #71 | 114 | 6.5%
Project #231 | 115.5 | 6.6%
Project #642 | 115.5 | 6.7%
Project #66 | 115.5 | 6.8%
Project #585 | 115.5 | 6.9%
Project #474 | 115.5 | 7%
Project #849 | 115.5 | 7.1%
Project #753 | 115.5 | 7.2%
Project #99 | 115.5 | 7.3%
Project #93 | 115.5 | 7.4%
Project #221 | 117 | 7.5%
Project #467 | 117 | 7.6%
Project #507 | 117 | 7.7%
Project #537 | 117 | 7.8%
Project #981 | 117 | 7.9%
Project #199 | 118.5 | 8%
Project #42 | 118.5 | 8.1%
Project #775 | 118.5 | 8.2%
Project #87 | 118.5 | 8.3%
Project #194 | 120 | 8.4%
Project #116 | 120 | 8.5%
Project #525 | 120 | 8.6%
Project #800 | 120 | 8.7%
Project #950 | 120 | 8.8%
Project #722 | 120 | 8.9%
Project #634 | 121.5 | 9%
Project #61 | 121.5 | 9.1%
Project #509 | 121.5 | 9.2%
Project #740 | 121.5 | 9.3%
Project #80 | 121.5 | 9.4%
Project #219 | 123 | 9.5%
Project #358 | 123 | 9.6%
Project #143 | 123 | 9.7%
Project #56 | 123 | 9.8%
Project #610 | 123 | 9.9%
Project #747 | 123 | 10%
Project #761 | 123 | 10.1%
Project #76 | 123 | 10.2%
Project #708 | 123 | 10.3%
Project #174 | 124.5 | 10.4%
Project #342 | 124.5 | 10.5%
Project #329 | 124.5 | 10.6%
Project #398 | 124.5 | 10.7%
Project #331 | 124.5 | 10.8%
Project #144 | 124.5 | 10.9%
Project #180 | 124.5 | 11%
Project #937 | 124.5 | 11.1%
Project #272 | 126 | 11.2%
Project #217 | 126 | 11.3%
Project #568 | 126 | 11.4%
Project #616 | 126 | 11.5%
Project #782 | 126 | 11.6%
Project #909 | 126 | 11.7%
Project #733 | 126 | 11.8%
Project #345 | 127.5 | 11.9%
Project #316 | 127.5 | 12%
Project #681 | 127.5 | 12.1%
Project #834 | 127.5 | 12.2%
Project #903 | 127.5 | 12.3%
Project #749 | 127.5 | 12.4%
Project #703 | 127.5 | 12.5%
Project #73 | 127.5 | 12.6%
Project #925 | 127.5 | 12.7%
Project #248 | 129 | 12.8%
Project #363 | 129 | 12.9%
Project #299 | 129 | 13%
Project #458 | 129 | 13.1%
Project #86 | 129 | 13.2%
Project #924 | 129 | 13.3%
Project #987 | 129 | 13.4%
Project #822 | 129 | 13.5%
Project #914 | 129 | 13.6%
Project #979 | 129 | 13.7%
Project #768 | 129 | 13.8%
Project #70 | 129 | 13.9%
Project #254 | 130.5 | 14%
Project #253 | 130.5 | 14.1%
Project #302 | 130.5 | 14.2%
Project #267 | 130.5 | 14.3%
Project #395 | 130.5 | 14.4%
Project #621 | 130.5 | 14.5%
Project #489 | 130.5 | 14.6%
Project #69 | 130.5 | 14.7%
Project #602 | 130.5 | 14.8%
Project #60 | 130.5 | 14.9%
Project #408 | 130.5 | 15%
Project #655 | 130.5 | 15.1%
Project #651 | 130.5 | 15.2%
Project #783 | 130.5 | 15.3%
Project #868 | 130.5 | 15.4%
Project #823 | 130.5 | 15.5%
Project #983 | 130.5 | 15.6%
Project #727 | 130.5 | 15.7%
Project #102 | 132 | 15.8%
Project #206 | 132 | 15.9%
Project #685 | 132 | 16%
Project #644 | 132 | 16.1%
Project #657 | 132 | 16.2%
Project #561 | 132 | 16.3%
Project #597 | 132 | 16.4%
Project #464 | 132 | 16.5%
Project #999 | 132 | 16.6%
Project #78 | 132 | 16.7%
Project #799 | 132 | 16.8%
Project #913 | 132 | 16.9%
Project #146 | 133.5 | 17%
Project #192 | 133.5 | 17.1%
Project #354 | 133.5 | 17.2%
Project #384 | 133.5 | 17.3%
Project #123 | 133.5 | 17.4%
Project #134 | 133.5 | 17.5%
Project #289 | 133.5 | 17.6%
Project #653 | 133.5 | 17.7%
Project #944 | 133.5 | 17.8%
Project #953 | 133.5 | 17.9%
Project #780 | 133.5 | 18%
Project #249 | 135 | 18.1%
Project #304 | 135 | 18.2%
Project #374 | 135 | 18.3%
Project #305 | 135 | 18.4%
Project #647 | 135 | 18.5%
Project #482 | 135 | 18.6%
Project #825 | 135 | 18.7%
Project #911 | 135 | 18.8%
Project #900 | 135 | 18.9%
Project #732 | 135 | 19%
Project #917 | 135 | 19.1%
Project #82 | 135 | 19.2%
Project #325 | 136.5 | 19.3%
Project #399 | 136.5 | 19.4%
Project #459 | 136.5 | 19.5%
Project #412 | 136.5 | 19.6%
Project #629 | 136.5 | 19.7%
Project #400 | 136.5 | 19.8%
Project #949 | 136.5 | 19.9%
Project #955 | 136.5 | 20%
Project #851 | 136.5 | 20.1%
Project #958 | 136.5 | 20.2%
Project #214 | 138 | 20.3%
Project #165 | 138 | 20.4%
Project #215 | 138 | 20.5%
Project #184 | 138 | 20.6%
Project #491 | 138 | 20.7%
Project #603 | 138 | 20.8%
Project #587 | 138 | 20.9%
Project #6 | 138 | 21%
Project #589 | 138 | 21.1%
Project #516 | 138 | 21.2%
Project #626 | 138 | 21.3%
Project #545 | 138 | 21.4%
Project #774 | 138 | 21.5%
Project #741 | 138 | 21.6%
Project #882 | 138 | 21.7%
Project #793 | 138 | 21.8%
Project #198 | 139.5 | 21.9%
Project #306 | 139.5 | 22%
Project #185 | 139.5 | 22.1%
Project #411 | 139.5 | 22.2%
Project #691 | 139.5 | 22.3%
Project #472 | 139.5 | 22.4%
Project #508 | 139.5 | 22.5%
Project #637 | 139.5 | 22.6%
Project #488 | 139.5 | 22.7%
Project #557 | 139.5 | 22.8%
Project #630 | 139.5 | 22.9%
Project #521 | 139.5 | 23%
Project #635 | 139.5 | 23.1%
Project #840 | 139.5 | 23.2%
Project #832 | 139.5 | 23.3%
Project #980 | 139.5 | 23.4%
Project #758 | 139.5 | 23.5%
Project #77 | 139.5 | 23.6%
Project #959 | 139.5 | 23.7%
Project #255 | 141 | 23.8%
Project #276 | 141 | 23.9%
Project #310 | 141 | 24%
Project #202 | 141 | 24.1%
Project #477 | 141 | 24.2%
Project #517 | 141 | 24.3%
Project #51 | 141 | 24.4%
Project #975 | 141 | 24.5%
Project #763 | 141 | 24.6%
Project #960 | 141 | 24.7%
Project #89 | 141 | 24.8%
Project #74 | 141 | 24.9%
Project #784 | 141 | 25%
Project #243 | 142.5 | 25.1%
Project #212 | 142.5 | 25.2%
Project #604 | 142.5 | 25.3%
Project #416 | 142.5 | 25.4%
Project #427 | 142.5 | 25.5%
Project #652 | 142.5 | 25.6%
Project #875 | 142.5 | 25.7%
Project #874 | 142.5 | 25.8%
Project #998 | 142.5 | 25.9%
Project #258 | 144 | 26%
Project #228 | 144 | 26.1%
Project #126 | 144 | 26.2%
Project #360 | 144 | 26.3%
Project #343 | 144 | 26.4%
Project #246 | 144 | 26.5%
Project #341 | 144 | 26.6%
Project #328 | 144 | 26.7%
Project #461 | 144 | 26.8%
Project #584 | 144 | 26.9%
Project #497 | 144 | 27%
Project #663 | 144 | 27.1%
Project #534 | 144 | 27.2%
Project #476 | 144 | 27.3%
Project #554 | 144 | 27.4%
Project #795 | 144 | 27.5%
Project #133 | 145.5 | 27.6%
Project #2 | 145.5 | 27.7%
Project #378 | 145.5 | 27.8%
Project #181 | 145.5 | 27.9%
Project #268 | 145.5 | 28%
Project #336 | 145.5 | 28.1%
Project #45 | 145.5 | 28.2%
Project #662 | 145.5 | 28.3%
Project #590 | 145.5 | 28.4%
Project #457 | 145.5 | 28.5%
Project #63 | 145.5 | 28.6%
Project #641 | 145.5 | 28.7%
Project #856 | 145.5 | 28.8%
Project #748 | 145.5 | 28.9%
Project #908 | 145.5 | 29%
Project #702 | 145.5 | 29.1%
Project #714 | 145.5 | 29.2%
Project #756 | 145.5 | 29.3%
Project #290 | 147 | 29.4%
Project #235 | 147 | 29.5%
Project #19 | 147 | 29.6%
Project #101 | 147 | 29.7%
Project #283 | 147 | 29.8%
Project #275 | 147 | 29.9%
Project #234 | 147 | 30%
Project #376 | 147 | 30.1%
Project #624 | 147 | 30.2%
Project #601 | 147 | 30.3%
Project #410 | 147 | 30.4%
Project #494 | 147 | 30.5%
Project #581 | 147 | 30.6%
Project #724 | 147 | 30.7%
Project #923 | 147 | 30.8%
Project #969 | 147 | 30.9%
Project #968 | 147 | 31%
Project #100 | 148.5 | 31.1%
Project #370 | 148.5 | 31.2%
Project #543 | 148.5 | 31.3%
Project #438 | 148.5 | 31.4%
Project #519 | 148.5 | 31.5%
Project #666 | 148.5 | 31.6%
Project #478 | 148.5 | 31.7%
Project #678 | 148.5 | 31.8%
Project #551 | 148.5 | 31.9%
Project #669 | 148.5 | 32%
Project #694 | 148.5 | 32.1%
Project #734 | 148.5 | 32.2%
Project #791 | 148.5 | 32.3%
Project #905 | 148.5 | 32.4%
Project #954 | 148.5 | 32.5%
Project #739 | 148.5 | 32.6%
Project #31 | 150 | 32.7%
Project #270 | 150 | 32.8%
Project #251 | 150 | 32.9%
Project #566 | 150 | 33%
Project #622 | 150 | 33.1%
Project #547 | 150 | 33.2%
Project #403 | 150 | 33.3%
Project #796 | 150 | 33.4%
Project #760 | 150 | 33.5%
Project #809 | 150 | 33.6%
Project #921 | 150 | 33.7%
Project #750 | 150 | 33.8%
Project #711 | 150 | 33.9%
Project #829 | 150 | 34%
Project #996 | 150 | 34.1%
Project #176 | 151.5 | 34.2%
Project #177 | 151.5 | 34.3%
Project #368 | 151.5 | 34.4%
Project #160 | 151.5 | 34.5%
Project #140 | 151.5 | 34.6%
Project #28 | 151.5 | 34.7%
Project #15 | 151.5 | 34.8%
Project #208 | 151.5 | 34.9%
Project #379 | 151.5 | 35%
Project #515 | 151.5 | 35.1%
Project #638 | 151.5 | 35.2%
Project #608 | 151.5 | 35.3%
Project #523 | 151.5 | 35.4%
Project #562 | 151.5 | 35.5%
Project #401 | 151.5 | 35.6%
Project #699 | 151.5 | 35.7%
Project #891 | 151.5 | 35.8%
Project #995 | 151.5 | 35.9%
Project #804 | 151.5 | 36%
Project #815 | 151.5 | 36.1%
Project #824 | 151.5 | 36.2%
Project #871 | 151.5 | 36.3%
Project #737 | 151.5 | 36.4%
Project #934 | 151.5 | 36.5%
Project #350 | 153 | 36.6%
Project #147 | 153 | 36.7%
Project #320 | 153 | 36.8%
Project #357 | 153 | 36.9%
Project #119 | 153 | 37%
Project #233 | 153 | 37.1%
Project #161 | 153 | 37.2%
Project #127 | 153 | 37.3%
Project #549 | 153 | 37.4%
Project #473 | 153 | 37.5%
Project #423 | 153 | 37.6%
Project #594 | 153 | 37.7%
Project #665 | 153 | 37.8%
Project #560 | 153 | 37.9%
Project #404 | 153 | 38%
Project #580 | 153 | 38.1%
Project #860 | 153 | 38.2%
Project #790 | 153 | 38.3%
Project #991 | 153 | 38.4%
Project #91 | 153 | 38.5%
Project #777 | 153 | 38.6%
Project #149 | 154.5 | 38.7%
Project #220 | 154.5 | 38.8%
Project #387 | 154.5 | 38.9%
Project #475 | 154.5 | 39%
Project #591 | 154.5 | 39.1%
Project #628 | 154.5 | 39.2%
Project #504 | 154.5 | 39.3%
Project #893 | 154.5 | 39.4%
Project #812 | 154.5 | 39.5%
Project #836 | 154.5 | 39.6%
Project #896 | 154.5 | 39.7%
Project #801 | 154.5 | 39.8%
Project #725 | 154.5 | 39.9%
Project #114 | 156 | 40%
Project #364 | 156 | 40.1%
Project #24 | 156 | 40.2%
Project #247 | 156 | 40.3%
Project #311 | 156 | 40.4%
Project #348 | 156 | 40.5%
Project #287 | 156 | 40.6%
Project #526 | 156 | 40.7%
Project #631 | 156 | 40.8%
Project #498 | 156 | 40.9%
Project #539 | 156 | 41%
Project #689 | 156 | 41.1%
Project #452 | 156 | 41.2%
Project #625 | 156 | 41.3%
Project #533 | 156 | 41.4%
Project #876 | 156 | 41.5%
Project #820 | 156 | 41.6%
Project #927 | 156 | 41.7%
Project #989 | 156 | 41.8%
Project #14 | 157.5 | 41.9%
Project #124 | 157.5 | 42%
Project #391 | 157.5 | 42.1%
Project #186 | 157.5 | 42.2%
Project #110 | 157.5 | 42.3%
Project #282 | 157.5 | 42.4%
Project #193 | 157.5 | 42.5%
Project #389 | 157.5 | 42.6%
Project #569 | 157.5 | 42.7%
Project #443 | 157.5 | 42.8%
Project #65 | 157.5 | 42.9%
Project #529 | 157.5 | 43%
Project #670 | 157.5 | 43.1%
Project #79 | 157.5 | 43.2%
Project #922 | 157.5 | 43.3%
Project #956 | 157.5 | 43.4%
Project #936 | 157.5 | 43.5%
Project #819 | 157.5 | 43.6%
Project #877 | 157.5 | 43.7%
Project #751 | 157.5 | 43.8%
Project #736 | 157.5 | 43.9%
Project #298 | 159 | 44%
Project #135 | 159 | 44.1%
Project #326 | 159 | 44.2%
Project #25 | 159 | 44.3%
Project #162 | 159 | 44.4%
Project #319 | 159 | 44.5%
Project #600 | 159 | 44.6%
Project #696 | 159 | 44.7%
Project #486 | 159 | 44.8%
Project #470 | 159 | 44.9%
Project #540 | 159 | 45%
Project #58 | 159 | 45.1%
Project #449 | 159 | 45.2%
Project #405 | 159 | 45.3%
Project #890 | 159 | 45.4%
Project #738 | 159 | 45.5%
Project #767 | 159 | 45.6%
Project #752 | 159 | 45.7%
Project #974 | 159 | 45.8%
Project #967 | 159 | 45.9%
Project #257 | 160.5 | 46%
Project #218 | 160.5 | 46.1%
Project #182 | 160.5 | 46.2%
Project #355 | 160.5 | 46.3%
Project #167 | 160.5 | 46.4%
Project #484 | 160.5 | 46.5%
Project #514 | 160.5 | 46.6%
Project #503 | 160.5 | 46.7%
Project #4 | 160.5 | 46.8%
Project #897 | 160.5 | 46.9%
Project #96 | 160.5 | 47%
Project #107 | 162 | 47.1%
Project #216 | 162 | 47.2%
Project #274 | 162 | 47.3%
Project #284 | 162 | 47.4%
Project #188 | 162 | 47.5%
Project #37 | 162 | 47.6%
Project #402 | 162 | 47.7%
Project #648 | 162 | 47.8%
Project #661 | 162 | 47.9%
Project #424 | 162 | 48%
Project #506 | 162 | 48.1%
Project #468 | 162 | 48.2%
Project #677 | 162 | 48.3%
Project #858 | 162 | 48.4%
Project #951 | 162 | 48.5%
Project #915 | 162 | 48.6%
Project #729 | 162 | 48.7%
Project #773 | 162 | 48.8%
Project #946 | 162 | 48.9%
Project #709 | 162 | 49%
Project #159 | 163.5 | 49.1%
Project #118 | 163.5 | 49.2%
Project #312 | 163.5 | 49.3%
Project #294 | 163.5 | 49.4%
Project #3 | 163.5 | 49.5%
Project #22 | 163.5 | 49.6%
Project #499 | 163.5 | 49.7%
Project #613 | 163.5 | 49.8%
Project #414 | 163.5 | 49.9%
Project #415 | 163.5 | 50%
Project #695 | 163.5 | 50.1%
Project #640 | 163.5 | 50.2%
Project #719 | 163.5 | 50.3%
Project #94 | 163.5 | 50.4%
Project #933 | 163.5 | 50.5%
Project #938 | 163.5 | 50.6%
Project #787 | 163.5 | 50.7%
Project #723 | 163.5 | 50.8%
Project #866 | 163.5 | 50.9%
Project #972 | 163.5 | 51%
Project #717 | 163.5 | 51.1%
Project #211 | 165 | 51.2%
Project #23 | 165 | 51.3%
Project #153 | 165 | 51.4%
Project #190 | 165 | 51.5%
Project #317 | 165 | 51.6%
Project #209 | 165 | 51.7%
Project #688 | 165 | 51.8%
Project #552 | 165 | 51.9%
Project #682 | 165 | 52%
Project #437 | 165 | 52.1%
Project #542 | 165 | 52.2%
Project #757 | 165 | 52.3%
Project #835 | 165 | 52.4%
Project #930 | 165 | 52.5%
Project #242 | 166.5 | 52.6%
Project #229 | 166.5 | 52.7%
Project #295 | 166.5 | 52.8%
Project #1000 | 166.5 | 52.9%
Project #27 | 166.5 | 53%
Project #187 | 166.5 | 53.1%
Project #646 | 166.5 | 53.2%
Project #548 | 166.5 | 53.3%
Project #451 | 166.5 | 53.4%
Project #575 | 166.5 | 53.5%
Project #465 | 166.5 | 53.6%
Project #463 | 166.5 | 53.7%
Project #766 | 166.5 | 53.8%
Project #982 | 166.5 | 53.9%
Project #984 | 166.5 | 54%
Project #854 | 166.5 | 54.1%
Project #963 | 166.5 | 54.2%
Project #811 | 166.5 | 54.3%
Project #894 | 166.5 | 54.4%
Project #130 | 168 | 54.5%
Project #154 | 168 | 54.6%
Project #205 | 168 | 54.7%
Project #121 | 168 | 54.8%
Project #163 | 168 | 54.9%
Project #339 | 168 | 55%
Project #150 | 168 | 55.1%
Project #490 | 168 | 55.2%
Project #520 | 168 | 55.3%
Project #46 | 168 | 55.4%
Project #746 | 168 | 55.5%
Project #852 | 168 | 55.6%
Project #754 | 168 | 55.7%
Project #976 | 168 | 55.8%
Project #883 | 168 | 55.9%
Project #291 | 169.5 | 56%
Project #366 | 169.5 | 56.1%
Project #145 | 169.5 | 56.2%
Project #595 | 169.5 | 56.3%
Project #609 | 169.5 | 56.4%
Project #692 | 169.5 | 56.5%
Project #512 | 169.5 | 56.6%
Project #418 | 169.5 | 56.7%
Project #636 | 169.5 | 56.8%
Project #966 | 169.5 | 56.9%
Project #932 | 169.5 | 57%
Project #884 | 169.5 | 57.1%
Project #72 | 169.5 | 57.2%
Project #964 | 169.5 | 57.3%
Project #713 | 169.5 | 57.4%
Project #9 | 169.5 | 57.5%
Project #122 | 171 | 57.6%
Project #132 | 171 | 57.7%
Project #111 | 171 | 57.8%
Project #535 | 171 | 57.9%
Project #611 | 171 | 58%
Project #41 | 171 | 58.1%
Project #656 | 171 | 58.2%
Project #659 | 171 | 58.3%
Project #460 | 171 | 58.4%
Project #53 | 171 | 58.5%
Project #632 | 171 | 58.6%
Project #573 | 171 | 58.7%
Project #928 | 171 | 58.8%
Project #817 | 171 | 58.9%
Project #997 | 171 | 59%
Project #965 | 171 | 59.1%
Project #95 | 171 | 59.2%
Project #264 | 172.5 | 59.3%
Project #250 | 172.5 | 59.4%
Project #230 | 172.5 | 59.5%
Project #33 | 172.5 | 59.6%
Project #263 | 172.5 | 59.7%
Project #36 | 172.5 | 59.8%
Project #238 | 172.5 | 59.9%
Project #593 | 172.5 | 60%
Project #57 | 172.5 | 60.1%
Project #615 | 172.5 | 60.2%
Project #480 | 172.5 | 60.3%
Project #618 | 172.5 | 60.4%
Project #764 | 172.5 | 60.5%
Project #862 | 172.5 | 60.6%
Project #813 | 172.5 | 60.7%
Project #88 | 172.5 | 60.8%
Project #971 | 172.5 | 60.9%
Project #125 | 174 | 61%
Project #179 | 174 | 61.1%
Project #245 | 174 | 61.2%
Project #277 | 174 | 61.3%
Project #131 | 174 | 61.4%
Project #20 | 174 | 61.5%
Project #390 | 174 | 61.6%
Project #431 | 174 | 61.7%
Project #447 | 174 | 61.8%
Project #59 | 174 | 61.9%
Project #55 | 174 | 62%
Project #440 | 174 | 62.1%
Project #759 | 174 | 62.2%
Project #803 | 174 | 62.3%
Project #779 | 174 | 62.4%
Project #942 | 174 | 62.5%
Project #718 | 174 | 62.6%
Project #334 | 175.5 | 62.7%
Project #337 | 175.5 | 62.8%
Project #396 | 175.5 | 62.9%
Project #191 | 175.5 | 63%
Project #406 | 175.5 | 63.1%
Project #650 | 175.5 | 63.2%
Project #935 | 175.5 | 63.3%
Project #705 | 175.5 | 63.4%
Project #845 | 175.5 | 63.5%
Project #865 | 175.5 | 63.6%
Project #108 | 177 | 63.7%
Project #286 | 177 | 63.8%
Project #128 | 177 | 63.9%
Project #645 | 177 | 64%
Project #550 | 177 | 64.1%
Project #501 | 177 | 64.2%
Project #538 | 177 | 64.3%
Project #830 | 177 | 64.4%
Project #700 | 177 | 64.5%
Project #721 | 177 | 64.6%
Project #881 | 177 | 64.7%
Project #772 | 177 | 64.8%
Project #371 | 178.5 | 64.9%
Project #307 | 178.5 | 65%
Project #309 | 178.5 | 65.1%
Project #204 | 178.5 | 65.2%
Project #352 | 178.5 | 65.3%
Project #280 | 178.5 | 65.4%
Project #397 | 178.5 | 65.5%
Project #40 | 178.5 | 65.6%
Project #425 | 178.5 | 65.7%
Project #952 | 178.5 | 65.8%
Project #863 | 178.5 | 65.9%
Project #846 | 178.5 | 66%
Project #720 | 178.5 | 66.1%
Project #878 | 178.5 | 66.2%
Project #898 | 178.5 | 66.3%
Project #743 | 178.5 | 66.4%
Project #213 | 180 | 66.5%
Project #381 | 180 | 66.6%
Project #175 | 180 | 66.7%
Project #106 | 180 | 66.8%
Project #172 | 180 | 66.9%
Project #21 | 180 | 67%
Project #330 | 180 | 67.1%
Project #313 | 180 | 67.2%
Project #479 | 180 | 67.3%
Project #496 | 180 | 67.4%
Project #679 | 180 | 67.5%
Project #572 | 180 | 67.6%
Project #528 | 180 | 67.7%
Project #419 | 180 | 67.8%
Project #421 | 180 | 67.9%
Project #579 | 180 | 68%
Project #895 | 180 | 68.1%
Project #945 | 180 | 68.2%
Project #892 | 180 | 68.3%
Project #771 | 180 | 68.4%
Project #870 | 180 | 68.5%
Project #988 | 180 | 68.6%
Project #266 | 181.5 | 68.7%
Project #189 | 181.5 | 68.8%
Project #372 | 181.5 | 68.9%
Project #252 | 181.5 | 69%
Project #373 | 181.5 | 69.1%
Project #232 | 181.5 | 69.2%
Project #170 | 181.5 | 69.3%
Project #288 | 181.5 | 69.4%
Project #383 | 181.5 | 69.5%
Project #599 | 181.5 | 69.6%
Project #546 | 181.5 | 69.7%
Project #667 | 181.5 | 69.8%
Project #453 | 181.5 | 69.9%
Project #957 | 181.5 | 70%
Project #744 | 181.5 | 70.1%
Project #833 | 181.5 | 70.2%
Project #789 | 181.5 | 70.3%
Project #990 | 181.5 | 70.4%
Project #265 | 183 | 70.5%
Project #260 | 183 | 70.6%
Project #47 | 183 | 70.7%
Project #742 | 183 | 70.8%
Project #818 | 183 | 70.9%
Project #712 | 183 | 71%
Project #869 | 183 | 71.1%
Project #978 | 183 | 71.2%
Project #81 | 183 | 71.3%
Project #83 | 183 | 71.4%
Project #168 | 184.5 | 71.5%
Project #115 | 184.5 | 71.6%
Project #369 | 184.5 | 71.7%
Project #327 | 184.5 | 71.8%
Project #171 | 184.5 | 71.9%
Project #105 | 184.5 | 72%
Project #156 | 184.5 | 72.1%
Project #385 | 184.5 | 72.2%
Project #117 | 184.5 | 72.3%
Project #683 | 184.5 | 72.4%
Project #435 | 184.5 | 72.5%
Project #553 | 184.5 | 72.6%
Project #64 | 184.5 | 72.7%
Project #446 | 184.5 | 72.8%
Project #962 | 184.5 | 72.9%
Project #867 | 184.5 | 73%
Project #745 | 184.5 | 73.1%
Project #973 | 184.5 | 73.2%
Project #886 | 184.5 | 73.3%
Project #322 | 186 | 73.4%
Project #359 | 186 | 73.5%
Project #382 | 186 | 73.6%
Project #10 | 186 | 73.7%
Project #586 | 186 | 73.8%
Project #674 | 186 | 73.9%
Project #606 | 186 | 74%
Project #567 | 186 | 74.1%
Project #462 | 186 | 74.2%
Project #407 | 186 | 74.3%
Project #680 | 186 | 74.4%
Project #880 | 186 | 74.5%
Project #778 | 186 | 74.6%
Project #943 | 186 | 74.7%
Project #278 | 187.5 | 74.8%
Project #112 | 187.5 | 74.9%
Project #279 | 187.5 | 75%
Project #224 | 187.5 | 75.1%
Project #323 | 187.5 | 75.2%
Project #335 | 187.5 | 75.3%
Project #394 | 187.5 | 75.4%
Project #26 | 187.5 | 75.5%
Project #413 | 187.5 | 75.6%
Project #493 | 187.5 | 75.7%
Project #43 | 187.5 | 75.8%
Project #455 | 187.5 | 75.9%
Project #441 | 187.5 | 76%
Project #513 | 187.5 | 76.1%
Project #671 | 187.5 | 76.2%
Project #445 | 187.5 | 76.3%
Project #8 | 187.5 | 76.4%
Project #769 | 187.5 | 76.5%
Project #889 | 187.5 | 76.6%
Project #222 | 189 | 76.7%
Project #318 | 189 | 76.8%
Project #344 | 189 | 76.9%
Project #223 | 189 | 77%
Project #301 | 189 | 77.1%
Project #450 | 189 | 77.2%
Project #502 | 189 | 77.3%
Project #524 | 189 | 77.4%
Project #430 | 189 | 77.5%
Project #97 | 189 | 77.6%
Project #887 | 189 | 77.7%
Project #807 | 189 | 77.8%
Project #847 | 189 | 77.9%
Project #961 | 189 | 78%
Project #103 | 190.5 | 78.1%
Project #157 | 190.5 | 78.2%
Project #377 | 190.5 | 78.3%
Project #324 | 190.5 | 78.4%
Project #365 | 190.5 | 78.5%
Project #308 | 190.5 | 78.6%
Project #315 | 190.5 | 78.7%
Project #583 | 190.5 | 78.8%
Project #527 | 190.5 | 78.9%
Project #672 | 190.5 | 79%
Project #563 | 190.5 | 79.1%
Project #912 | 190.5 | 79.2%
Project #853 | 190.5 | 79.3%
Project #885 | 190.5 | 79.4%
Project #98 | 190.5 | 79.5%
Project #993 | 190.5 | 79.6%
Project #985 | 190.5 | 79.7%
Project #776 | 190.5 | 79.8%
Project #907 | 190.5 | 79.9%
Project #113 | 192 | 80%
Project #367 | 192 | 80.1%
Project #654 | 192 | 80.2%
Project #511 | 192 | 80.3%
Project #541 | 192 | 80.4%
Project #417 | 192 | 80.5%
Project #806 | 192 | 80.6%
Project #873 | 192 | 80.7%
Project #794 | 192 | 80.8%
Project #30 | 193.5 | 80.9%
Project #17 | 193.5 | 81%
Project #137 | 193.5 | 81.1%
Project #226 | 193.5 | 81.2%
Project #444 | 193.5 | 81.3%
Project #522 | 193.5 | 81.4%
Project #684 | 193.5 | 81.5%
Project #658 | 193.5 | 81.6%
Project #726 | 193.5 | 81.7%
Project #844 | 193.5 | 81.8%
Project #755 | 193.5 | 81.9%
Project #321 | 195 | 82%
Project #293 | 195 | 82.1%
Project #18 | 195 | 82.2%
Project #380 | 195 | 82.3%
Project #62 | 195 | 82.4%
Project #607 | 195 | 82.5%
Project #531 | 195 | 82.6%
Project #831 | 195 | 82.7%
Project #710 | 195 | 82.8%
Project #916 | 195 | 82.9%
Project #901 | 195 | 83%
Project #92 | 195 | 83.1%
Project #120 | 196.5 | 83.2%
Project #393 | 196.5 | 83.3%
Project #361 | 196.5 | 83.4%
Project #668 | 196.5 | 83.5%
Project #487 | 196.5 | 83.6%
Project #879 | 196.5 | 83.7%
Project #906 | 196.5 | 83.8%
Project #300 | 198 | 83.9%
Project #240 | 198 | 84%
Project #577 | 198 | 84.1%
Project #571 | 198 | 84.2%
Project #54 | 198 | 84.3%
Project #693 | 198 | 84.4%
Project #422 | 198 | 84.5%
Project #84 | 198 | 84.6%
Project #861 | 198 | 84.7%
Project #765 | 198 | 84.8%
Project #730 | 198 | 84.9%
Project #142 | 199.5 | 85%
Project #12 | 199.5 | 85.1%
Project #269 | 199.5 | 85.2%
Project #565 | 199.5 | 85.3%
Project #986 | 199.5 | 85.4%
Project #798 | 199.5 | 85.5%
Project #899 | 199.5 | 85.6%
Project #362 | 201 | 85.7%
Project #273 | 201 | 85.8%
Project #338 | 201 | 85.9%
Project #29 | 201 | 86%
Project #346 | 201 | 86.1%
Project #481 | 201 | 86.2%
Project #620 | 201 | 86.3%
Project #85 | 201 | 86.4%
Project #929 | 201 | 86.5%
Project #704 | 201 | 86.6%
Project #838 | 201 | 86.7%
Project #225 | 202.5 | 86.8%
Project #262 | 202.5 | 86.9%
Project #375 | 202.5 | 87%
Project #349 | 202.5 | 87.1%
Project #347 | 202.5 | 87.2%
Project #109 | 202.5 | 87.3%
Project #420 | 202.5 | 87.4%
Project #617 | 202.5 | 87.5%
Project #436 | 202.5 | 87.6%
Project #495 | 202.5 | 87.7%
Project #166 | 204 | 87.8%
Project #239 | 204 | 87.9%
Project #173 | 204 | 88%
Project #530 | 204 | 88.1%
Project #947 | 204 | 88.2%
Project #762 | 204 | 88.3%
Project #827 | 204 | 88.4%
Project #797 | 204 | 88.5%
Project #716 | 204 | 88.6%
Project #210 | 205.5 | 88.7%
Project #38 | 205.5 | 88.8%
Project #196 | 205.5 | 88.9%
Project #434 | 205.5 | 89%
Project #454 | 205.5 | 89.1%
Project #821 | 205.5 | 89.2%
Project #855 | 205.5 | 89.3%
Project #735 | 205.5 | 89.4%
Project #183 | 207 | 89.5%
Project #627 | 207 | 89.6%
Project #48 | 207 | 89.7%
Project #466 | 207 | 89.8%
Project #614 | 207 | 89.9%
Project #612 | 207 | 90%
Project #439 | 207 | 90.1%
Project #859 | 207 | 90.2%
Project #904 | 207 | 90.3%
Project #340 | 208.5 | 90.4%
Project #333 | 208.5 | 90.5%
Project #643 | 208.5 | 90.6%
Project #839 | 208.5 | 90.7%
Project #828 | 208.5 | 90.8%
Project #910 | 208.5 | 90.9%
Project #918 | 208.5 | 91%
Project #919 | 208.5 | 91.1%
Project #788 | 208.5 | 91.2%
Project #195 | 210 | 91.3%
Project #314 | 210 | 91.4%
Project #169 | 210 | 91.5%
Project #576 | 210 | 91.6%
Project #544 | 210 | 91.7%
Project #805 | 210 | 91.8%
Project #808 | 210 | 91.9%
Project #197 | 211.5 | 92%
Project #158 | 211.5 | 92.1%
Project #698 | 211.5 | 92.2%
Project #555 | 213 | 92.3%
Project #90 | 213 | 92.4%
Project #888 | 213 | 92.5%
Project #139 | 214.5 | 92.6%
Project #1 | 214.5 | 92.7%
Project #926 | 214.5 | 92.8%
Project #303 | 216 | 92.9%
Project #483 | 216 | 93%
Project #902 | 216 | 93.1%
Project #992 | 216 | 93.2%
Project #802 | 216 | 93.3%
Project #948 | 216 | 93.4%
Project #227 | 217.5 | 93.5%
Project #351 | 217.5 | 93.6%
Project #518 | 217.5 | 93.7%
Project #843 | 217.5 | 93.8%
Project #977 | 217.5 | 93.9%
Project #857 | 217.5 | 94%
Project #701 | 217.5 | 94.1%
Project #32 | 219 | 94.2%
Project #35 | 219 | 94.3%
Project #236 | 219 | 94.4%
Project #49 | 219 | 94.5%
Project #731 | 219 | 94.6%
Project #781 | 219 | 94.7%
Project #941 | 219 | 94.8%
Project #34 | 220.5 | 94.9%
Project #297 | 220.5 | 95%
Project #500 | 220.5 | 95.1%
Project #409 | 220.5 | 95.2%
Project #151 | 222 | 95.3%
Project #448 | 222 | 95.4%
Project #715 | 222 | 95.5%
Project #920 | 222 | 95.6%
Project #261 | 223.5 | 95.7%
Project #200 | 225 | 95.8%
Project #104 | 225 | 95.9%
Project #386 | 225 | 96%
Project #619 | 225 | 96.1%
Project #690 | 225 | 96.2%
Project #676 | 225 | 96.3%
Project #559 | 225 | 96.4%
Project #837 | 225 | 96.5%
Project #138 | 226.5 | 96.6%
Project #11 | 226.5 | 96.7%
Project #50 | 226.5 | 96.8%
Project #564 | 226.5 | 96.9%
Project #148 | 228 | 97%
Project #285 | 228 | 97.1%
Project #428 | 228 | 97.2%
Project #841 | 228 | 97.3%
Project #850 | 228 | 97.4%
Project #816 | 228 | 97.5%
Project #826 | 229.5 | 97.6%
Project #532 | 231 | 97.7%
Project #939 | 231 | 97.8%
Project #485 | 232.5 | 97.9%
Project #785 | 232.5 | 98%
Project #786 | 232.5 | 98.1%
Project #388 | 234 | 98.2%
Project #129 | 235.5 | 98.3%
Project #44 | 235.5 | 98.4%
Project #244 | 237 | 98.5%
Project #598 | 237 | 98.6%
Project #792 | 237 | 98.7%
Project #556 | 241.5 | 98.8%
Project #994 | 241.5 | 98.9%
Project #207 | 243 | 99%
Project #237 | 243 | 99.1%
Project #471 | 243 | 99.2%
Project #697 | 243 | 99.3%
Project #75 | 243 | 99.4%
Project #578 | 244.5 | 99.5%
Project #256 | 249 | 99.6%
Project #201 | 255 | 99.7%
Project #605 | 265.5 | 99.8%
Project #392 | 277.5 | 99.9%
Project #67 | 286.5 | 100%
Grand Total | 164.643